{"text_format":"1","workbook":"xlsx","n_sheets":20,"sheets":["Mainsheet","Completed","Calc","Areaofobs","Vessel_type","Deficiency_type","VIQrefno","Equipment_list","PSC_MOU","Inspection_type","Deficiency_Cause","Observer_code","Status_code","PSC_ref_no","Risk_value_of_obs","Year","Month","Date_","Sheet1","Ship_information"],"not_rendered":{"charts":0,"images":5,"macros":1,"external_links":0,"defined_names":12,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Mainsheet","index":0,"n_rows":41,"n_cols":27,"rows_kept":41,"cut":false,"hidden":false,"merged":[[12,6,12,26],[8,6,8,26],[10,8,10,9],[10,12,10,13]]}
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,"Defect - Damage Monitoring Sheet"]
[]
[null,null,null,null,null,null,null,"Date of Report","09-Oct-2019",null,null,"Ship Name","DHT EDELWEISS"]
[]
[]
[]
[]
[]
[null,null,null,null,"ID","UNIQUE ID","Date Recorded","Type of Deficiency","Observer code","Type of Inspection","Description of Deficiency","Equipment Categories","Area of Observation","Deficiency Cause","VIQ Ref Number","Risk Value of Obs","PSC Ref Number","PSC MOU ID","Action Taken or Required","Target Date","PO Ref No.","Status Code","Date Completed","Drydock","Info Sharing","Critical Item","Audit Type"]
[null,null,null,null,null,"2019-10-10T23:58:58","2019-02-10","Observation","Ship Staff","Ship Staff Insp.","Most of the PV valves on deck were found leaking.","Miscellaneous","Cargo / Ballast Systems","Equipment Related",8.19,"High","Not Applicable","Not Applicable","4 PV valves have been machined by shore and fitted back, 3 more has been landed for machining by shore.","2019-12-30",null,"In progress",null,"No",null,null,"External"]
[null,null,null,null,null,"2019-11-10T00:03:11","2019-05-15","Non Conformity","Ship Staff","Ship Staff Insp.","The IS telephone in pump room has no connection to bridge.","Miscellaneous","LSA / FFA Appliances","Equipment Related",5.27,"Medium","Not Applicable","Not Applicable","Mr Kamlesh Solanki is working on this issue as per mail from office dated 02 Aug 2019.","2019-12-30",null,"In progress",null,"No",null,null,"Internal"]
[null,null,null,null,null,"2019-11-10T00:06:15","2019-06-12","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Few gratings in the manifold area are wasted.","Deck Pipe / Fittings","General Appearance","Equipment Related",6.6,"Medium","Not Applicable","Not Applicable","RO raised for new grating, awaiting supply.","2019-11-15","DEDE190166","Waiting spare",null,"No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-11T00:16:29","2019-06-12","Observation","Owner / Marine / Tech. Suptd.","Ship Staff Insp.","Hose handling crane emergency pump operation.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related",8.5,"Medium","Not Applicable","Not Applicable","To check if job exists in PAL for regular check/routines.","2019-10-30",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-11T00:19:03","2019-08-12","Deficiency","Ship Staff","Ship Staff Insp.","High pressure hose for lifeboat air bottles found leaking.","LSA / FFA","LSA / FFA Appliances","Equipment Related",5.29,"High","Not Applicable","Not Applicable","RO raised for new hose, awaiting supply.","2019-10-28","DEDE190187","Waiting spare",null,"No",null,null,"Internal"]
[null,null,null,null,null,"2019-11-10T00:21:24","2019-08-25","Deficiency","Ship Staff","Ship Staff Insp.","Vapour manifold valves observed leaking.","Deck Pipe / Fittings","Cargo / Ballast Systems","Equipment Related",8.17,"Low","Not Applicable","Not Applicable","RO raised for new seat rings of the valves, awaiting supply.","2019-12-30","DEDE190184","Waiting spare",null,"No",null,null,"Internal"]
[null,null,null,null,null,"2019-11-10T00:24:39","2019-09-09","Observation","Ship Staff","Ship Staff Insp.","Water ingress was observed in W1, W2, M1 and M# winch / windlass gera oil box.","Mooring Mach.","Mooring","Equipment Related",9.14,"Medium","Not Applicable","Not Applicable","Gear oil of W1 and M3 renewed, ones new stock of gear oil is received, gera oil of W2 and M1 to be renewed.","2019-12-30",null,"In progress",null,"No",null,null,"Internal"]
[null,null,null,null,null,"2019-11-10T00:27:02","2019-09-15","Deficiency","Ship Staff","Ship Staff Insp.","3 nos. BA bottle cylinder valve were found leaking.","LSA / FFA","LSA / FFA Appliances","Equipment Related",5.43,"High","Not Applicable","Not Applicable","RO raised for new cylinder valves, awaiting supply.","2019-11-15","DEDE190209","Waiting spare",null,"No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-11T16:18:30","2018-11-28","Deficiency","Ship Staff","Ship Staff Insp.","No.1 Boiler main feed water regulating valve leaking","Boiler","Eng. / Strg. Comp.","Equipment Related",10.29,"Medium","Not Applicable","Not Applicable","Awaiting spares","2019-10-31","DEDE190053","Waiting spare",null,"No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-11T17:44:47","2019-05-11","Observation","Ship Staff","Ship Staff Insp.","16/7K steam pressure reducing controller defective","Boiler","Eng. / Strg. Comp.","Equipment Related",10.29,"Medium","Not Applicable","Not Applicable","To renew the controller","2019-10-30","DEDE190122","Waiting spare",null,"No",null,null,"Internal"]
[null,null,null,null,null,"2019-11-10T17:50:47","2019-06-12","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","AE #1 vibration noticed while in operation","Aux. Engine","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","Foundation resilient mountings clearance checked. Requisition for new mountings raised.","2019-11-08","DEDE190167","Waiting spare",null,"No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-11T21:03:33","2019-06-12","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","ACC AC no spare complete compressor","Miscellaneous","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","RO raised for one spare complete AC compressor","2019-10-30","DEDE190150","Waiting spare",null,"No",null,null,"Internal"]
[null,null,null,null,null,"2019-11-10T21:06:43","2019-06-12","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Few units FO recirc line non return valve reported leaking","Aux. Engine,Main Engine ","Eng. / Strg. Comp.","Equipment Related",10.29,"Medium","Not Applicable","Not Applicable","Requisition raised for new NR vlave","2019-10-30","DEDE190152","Waiting spare",null,"No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-11T21:10:27","2019-06-12","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","#1 AE LO cons high","Aux. Engine","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","HEAD DECARB COMPLETED 2 NOS LINERS TO REPLACE WITH SPARE","2019-10-30",null,"In progress",null,"No",null,null,"Internal"]
[null,null,null,null,null,"2019-11-10T21:13:50","2019-08-25","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Engine room audible alarm on COP platform was not operational","Miscellaneous","Eng. / Strg. Comp.","Equipment Related",10.29,"Medium","Not Applicable","Not Applicable","RO RAISED AWAITING SPARES","2019-10-31","DEDE190192","Waiting spare",null,"No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-11T21:16:39","2019-08-25","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","During first STS operation, while telegraph was on dead slow ahead (23 RPM), ME RPM was found fluctuating from 16 to 30 RPM. While attempt was made to reduce ME RPM to 20, ME stopped running. Thereafter for following TWO STS operations, ME was run at dead slow ahead (23 RPM). ","Main Engine ","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","ME tested at various RPM until 18 rpm and found fluctuation in engine rpm below 22 rpm. Same is in follow up with office in separate mail","2019-10-31",null,"In progress",null,"No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-11T21:19:17","2019-09-05","Observation","Ship Staff","Ship Staff Insp.","#1 AC compressor valve plate","Air Comp.","Eng. / Strg. Comp.","Equipment Related",10.29,"Medium","Not Applicable","Not Applicable","#1 AC compressor overhauled with new valves. Found valve plate has deep scorings in various places. Requisition being raised","2019-10-31","DEDE190224","Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-11T21:23:20","2019-09-09","Observation","Ship Staff","Ship Staff Insp.","#2 Bilge, Fire and GS pump found vibrating and leaking from mechanical seal","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",10.29,"Medium","Not Applicable","Not Applicable","Pump opened up found securing dowel pin of mouth ring sheared and has touched the bottom impeller. Impeller worn out in line of mouth ring. Line bearing found worn down, same replaced, mechanical seal renewed, pump boxed back, all connections fitted back. Pump in normal operation developing sufficient pressure without any vibration. Requisition for spares raised.","2019-10-31","DEDE190219","Waiting spare",null,"No",null,null,"Internal"]
[null,null,null,null,null,"2019-11-10T21:29:18","2019-09-15","Deficiency","Ship Staff","Ship Staff Insp.","#2 Boiler water circulating pump leaking from oil seal.","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",10.29,"Medium","Not Applicable","Not Applicable","Pump opened up found oil seal end cover lip worn out. No spare cover onboard. Requisition for spares raised.","2019-10-30","DEDE190218","Waiting spare",null,"No",null,null,"Internal"]
[null,null,null,null,null,"2019-12-10T07:03:38","2019-09-15","Observation","Ship Staff","Ship Staff Insp.","#1 Boiler atomizing steam valve leaking from bonnet.","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",10.29,"Medium","Not Applicable","Not Applicable","Valve checked found valve spindle threads on bonnet worn out. Spare valve requisition raised along with Engine stores","2019-10-31","DEDE190213","Waiting spare",null,"No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-12T07:07:43","2019-09-30","Deficiency","Ship Staff","Ship Staff Insp.","Various pressure and temperature gauges found error in readings after calibration","Deck Pipe / Fittings","Eng. / Strg. Comp.","Equipment Related",10.29,"Medium","Not Applicable","Not Applicable","RO raised for defective gauges and for spare","2019-10-31","DEDE190213","Waiting spare",null,"No",null,null,"Internal"]
[null,null,null,null,null,"2019-12-10T07:10:01","2019-10-05","Observation","Ship Staff","Ship Staff Insp.","Galley fat trap inlet gate valve disc damaged","Deck Pipe / Fittings","Eng. / Strg. Comp.","Equipment Related",10.29,"Medium","Not Applicable","Not Applicable","RO raised for valve","2019-10-31","DEDE190213","Waiting spare",null,"No",null,null,"Internal"]
[null,null,null,null,null,"2019-12-10T07:12:31","2019-10-05","Observation","Ship Staff","Ship Staff Insp.","AE jacket pre-heater pump leaking form seal","Aux. Engine","Eng. / Strg. Comp.","Equipment Related",10.29,"Medium","Not Applicable","Not Applicable","RO RAISED","2019-10-31","DEDE190179","Waiting spare",null,"No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-12T07:14:27","2019-10-09","Deficiency","Ship Staff","Ship Staff Insp.","Sewage collecting tank level gauge not operational","Miscellaneous","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","Found bob missing and spring on the level gauge damaged","2019-10-31","DEDE190244","Waiting spare",null,"No",null,null,"Internal"]

{"sheet":"Completed","index":1,"n_rows":123,"n_cols":27,"rows_kept":123,"cut":false,"hidden":false,"merged":[[8,6,8,26],[10,8,10,9],[10,12,10,13],[12,6,12,26]]}
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,"Defect - Damage Monitoring Sheet"]
[]
[null,null,null,null,null,null,null,"Date of Report","9-9-2019",null,null,"Ship Name","DHT EDELWEISS"]
[]
[]
[]
[]
[]
[null,null,null,null,"ID","UNIQUE ID","Date Recorded","Type of Deficiency","Observer code","Type of Inspection","Description of Deficiency","Equipment Categories","Area of Observation","Deficiency Cause","VIQ Ref Number","Risk Value of Obs","PSC Ref Number","PSC MOU ID","Action Taken or Required","Target Date","PO Ref No.","Status Code","Date Completed","Drydock","Info Sharing","Critical Item","Audit Type"]
[null,null,null,null,null,"2019-10-10T10:05:24","2018-08-15","Observation","Ship Staff","Ship Staff Insp.","Hyd remote valve box on deck ","Deck Pipe / Fittings","General Appearance","External Factors",11.4,"Very High","Not Applicable","Not Applicable","All hydraulic boxes de-rusted and painted","2018-12-15",null,"Completed","2019-01-14","No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T10:15:03","2018-12-30","Deficiency","Ship Staff","Ship Staff Insp.","VRC Unloading switch malfunction,unloader sometimes not working causing high hydraulic pressure which is activating high pressure alarm. ","Cargo Mach.","Cargo / Ballast Systems","Equipment Related",8.2100000000000009,"High","Not Applicable","Not Applicable","Received sapres parts and replaced.","2019-01-30",null,"Completed","2019-01-23","No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T11:01:59","2018-11-22","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","It was reported that port Windlass both mooring drum have a wobble, same to be added in DDRL for planning of repair","Deck Mach.","Mooring","Equipment Related",9.14,"Medium","Not Applicable","Not Applicable","Entered in REFMAN","2018-12-30",null,"Completed","2019-01-30","No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T11:05:38","2019-01-30","Deficiency","Ship Staff","Ship Staff Insp.","DO bunkering line on deck 2 x gaskets leaking","Deck Pipe / Fittings","General Appearance","Equipment Related",6.7,"High","Not Applicable","Not Applicable","Renew gaskets","2019-02-05",null,"Completed","2019-02-07","No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T11:11:49","2018-12-19","Deficiency","Ship Staff","Ship Staff Insp.","MF/HF shore acknowledgement not received","Elect. Mach. & Equip.","Communication","Equipment Related",4.2300000000000004,"High","Not Applicable","Not Applicable","Technician attended at Singapore for trouble shooting, Antenna replaced","2019-03-18",null,"Completed","2019-02-10","No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T11:23:43","2019-01-30","Deficiency","Ship Staff","Ship Staff Insp.","X-Band radar not working","Nav & comm. equip.","Navigation","Equipment Related",4.7,"High","Not Applicable","Not Applicable","Technician attended vessel in Singapore for trouble shooting, problem rectified","2019-02-09",null,"Completed","2019-02-10","No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T11:30:39","2019-02-10","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Steering room fire door kept open/tied rope","Miscellaneous","General Appearance","Human Error,Inappropriate Procedure",5.35,"Medium","Not Applicable","Not Applicable","Ropes removed ,door closed and all personnel briefed","2019-02-17",null,"Completed","2019-02-12","No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T11:34:32","2019-02-10","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Nozzles kept in the fire hose boxes found not clean","LSA / FFA","LSA / FFA Appliances","Behaviour Based,Human Error,Inappropriate Procedure",5.38,"High","Not Applicable","Not Applicable","To ensure all Nozzles were cleaned and kept ready for use","2019-03-10",null,"Completed","2019-02-13","No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T11:40:00","2018-12-30","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Vessel does not have one or two extinguishers with a total capacity of not less than 18 kg (for CO2)and 45 Kg(for DCP)","LSA / FFA","LSA / FFA Appliances","Human Error,Knowledge Based",5.42,"Medium","Not Applicable","Not Applicable","2 CO2 extinguishers of 9kg each received and replaced with old extinguishers","2019-01-30",null,"Completed","2019-02-13","No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T11:46:31","2019-02-10","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Reported that it’s time consuming, while attempting Mooring  Winch derusting/coating job – takes 4~5 days for 1 MW","Mooring Mach.","Mooring","Equipment Related,External Factors,Inappropriate Procedure",9.14,"Medium","Not Applicable","Not Applicable","Commenced using sand blaster","2019-04-10",null,"Completed","2019-02-13","No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T11:51:22","2018-12-19","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Air reducer to be fitted on Sea chest Pressure testing arranement in pumproom ","Cargo Mach.","Cargo / Ballast Systems","Inappropriate Procedure,Knowledge Based",6.4,"High","Not Applicable","Not Applicable","Pressure reducer fitted","2019-03-18",null,"Completed","2019-02-14","No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T11:54:34","2018-12-19","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Pressure gauges for AUS Pneumatic valve are not in good order.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related,External Factors",8.1300000000000008,"Medium","Not Applicable","Not Applicable","AUS pressure gauge renewed","2019-03-18",null,"Completed","2019-02-15","No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T11:58:00","2018-07-05","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Superficial crack on discharge hose of No-18 trolley foam fire extinguisher 45 litres type kept near emergency air compressor & 32. Suspect leakage from body of No-18 trolley foam fire extinguisher","LSA / FFA","LSA / FFA Appliances","Equipment Related,External Factors",5.42,"Medium","Not Applicable","Not Applicable","Replaced with new hose","2018-12-15",null,"Completed","2019-02-15","No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T12:40:11","2019-02-10","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Waste dust bin bottom rusted and spreading to floor in crew pantry","Miscellaneous","MLC Related","Human Error",11.13,"Low","Not Applicable","Not Applicable","Bin bottom derusted and painted.","2019-02-25",null,"Completed","2019-02-20","No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T12:44:55","2019-02-10","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Gangway air motor lubricator dry-no oil/Moisture drain not drained.","Deck Mach.","General Appearance","Human Error",5.47,"Medium","Not Applicable","Not Applicable","Lubricator moisture removed,oil filled to 80% capacity pf the cup.","2019-02-17",null,"Completed","2019-02-24","No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T12:49:32","2018-12-19","Deficiency","Ship Staff","Ship Staff Insp.","EEBD Mask damaged","LSA / FFA","LSA / FFA Appliances","Equipment Related",5.44,"High","Not Applicable","Not Applicable","Spares received","2019-03-18",null,"Completed","2019-02-25","No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T12:53:24","2019-02-10","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Pumproom davit slewing gear guard plate holed","Deck Mach.","General Appearance","Equipment Related",11.1,"High","Not Applicable","Not Applicable","Slewing gear guard plate  fabricated new  and installed.","2019-03-10",null,"Completed","2019-02-28","No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T12:58:22","2018-11-27","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Both winch clutch engaging/disengaging safety (hydraulic) inoperational.","Mooring Mach.","Mooring","Equipment Related",9.1999999999999993,"Medium","Not Applicable","Not Applicable","Both winch clutch engaging/disengaging safety safety limit switch de-rusted and freely moving now.l","2019-02-22",null,"Completed","2019-02-28","No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T13:01:25","2019-02-10","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Flood light mast above midship store cable pipe rusty.","Deck Pipe / Fittings","General Appearance","External Factors",11.9,null,"Not Applicable","Not Applicable","Derusted and painted.","2019-03-10",null,"Completed","2019-02-28","No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T13:05:02","2019-02-10","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Flood light mast on deck,cable stays not sufficiently greased to protect from rust.","Deck Pipe / Fittings","General Appearance","Inappropriate Procedure",11.9,null,"Not Applicable","Not Applicable","Sufficient grease applied on mast stays.","2019-02-17",null,"Completed","2019-02-28","No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T13:07:57","2019-02-10","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Life boat davit wire reel drum-rusty at the edges.","LSA / FFA","LSA / FFA Appliances","Human Error",5.29,"High","Not Applicable","Not Applicable","Derusted and painiting carried out.","2019-02-25",null,"Completed","2019-02-25","No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T13:25:51","2019-01-12","Deficiency","Ship Staff","Ship Staff Insp.","Aft draft showing 30cm more value than actual/visual draft.","Miscellaneous","Cargo / Ballast Systems","Equipment Related",8.1300000000000008,"Medium","Not Applicable","Not Applicable","Aft draft guage calibrated and adjusted.","2019-04-01",null,"Completed","2019-03-01","No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T13:28:31","2019-02-10","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Pumproom motor casing/body fin rusted.","Deck Mach.","Cargo / Ballast Systems","Equipment Related",11.1,"High","Not Applicable","Not Applicable","Derusted and painted.","2019-03-10",null,"Completed","2019-03-07","No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T13:30:53","2018-08-15","Deficiency","Ship Staff","Ship Staff Insp.","Foam monitors leaking","LSA / FFA","LSA / FFA Appliances","Equipment Related",5.35,"Medium","Not Applicable","Not Applicable","Job completed-Overhauled","2019-02-22",null,"Completed","2019-03-02","No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T13:33:45","2019-02-10","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Mooring winch brake band stopper bolt clearance high","Mooring Mach.","Mooring","Equipment Related",9.15,"Medium","Not Applicable","Not Applicable","Adjusted all mooring winch brake band stiopper bolt.","2019-02-25",null,"Completed","2019-03-07","No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T13:37:30","2019-02-10","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Port and starboard windlass looks rusty/dirty,standing platform gratings rusty.","Mooring Mach.","General Appearance","External Factors",9.14,"Medium","Not Applicable","Not Applicable","Derusted and painted.","2019-03-10",null,"Completed","2019-02-25","No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T13:40:18","2018-12-19","Deficiency","Ship Staff","Ship Staff Insp.","Air horn for pumproom gas detection system is broken.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related",5.17,"Very High","Not Applicable","Not Applicable","Same been attended and fixed.","2019-03-13",null,"Completed","2019-04-02","No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T13:43:44","2019-02-10","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Washed boiler suits lying in a heap,waste rags lying near one discarded w/machine .","Miscellaneous","General Appearance","Human Error",11.13,"Low","Not Applicable","Not Applicable","Fabricated stowing racks for boiler suits to maintain cleaniliness/house keeping.","2019-02-17",null,"Completed","2019-04-06","No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T14:26:07","2018-07-05","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Plunger for nozzle of 25kg DCPX2 extinguisher for helicopter damaged.","LSA / FFA","LSA / FFA Appliances","Equipment Related",5.42,"Medium","Not Applicable","Not Applicable","RO raised Recieved spares","2018-12-15","DEDE190097","Completed","2019-04-21","No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T20:20:22","2019-02-10","Observation","Ship Staff","Ship Staff Insp.","DGPS#2  navigator changeover switch fault","Elect. Mach. & Equip.","Navigation","Equipment Related",4.7,"High","Not Applicable","Not Applicable","Technician attended in Singapore for trouble shooting, but model of GPS and RADAR is not compatible","2019-04-30",null,"Completed","2019-04-21","No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T20:23:43","2018-12-19","Deficiency","Ship Staff","Ship Staff Insp.","VDR – X band radar image duplicating and recording intermittently","Nav & comm. equip.","Navigation","Equipment Related",4.7,"High","Not Applicable","Not Applicable","Awaiting technician for trouble shooting","2019-03-30",null,"Completed","2019-04-21","No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T20:29:02","2019-02-10","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Fwd side Port holes, lot of window sills has corrosion marks/coating failure","Accommodation ","General Appearance","Equipment Related,External Factors",11.6,"Medium","Not Applicable","Not Applicable","To plan to derust and paint during long voyage","2019-04-10",null,"Completed","2019-04-29","No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T20:31:50","2019-02-10","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Bridge wing under sides, support pillars/frames has scattered rust spots","Accommodation ","General Appearance","Equipment Related,External Factors",11.6,"Medium","Not Applicable","Not Applicable","To plan to spot derust and paint","2019-05-10",null,"Completed","2019-04-29","No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T20:36:29","2019-02-10","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Noticed ginger rust forming at the foundation/base on deck standing structure ","Accommodation ","General Appearance","Equipment Related,External Factors",11.4,"Very High","Not Applicable","Not Applicable","To ensure this is periodically attended to and weekly washing is done","2019-04-10",null,"Completed","2019-04-29","No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T20:40:13","2019-02-10","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Pipe stack on deck under supports/angle frame had started rusting in locations near to accom block","Deck Pipe / Fittings","General Appearance","Equipment Related,External Factors",11.4,"Very High","Not Applicable","Not Applicable","Same to be immediately attended, spot drust/paint – weekly washing of pipe stacks to be diligently followed to avoid rust setting in","2019-04-10",null,"Completed","2019-04-25","No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T20:43:21","2019-02-10","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Pinting on funnel looking dull","Hull & Tanks","General Appearance","Equipment Related,External Factors",11.3,"Medium","Not Applicable","Not Applicable","To wash with Oxalic acid and see if appearance improves, else to plan for a full coat","2019-04-10",null,"Completed","2019-04-25","No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T20:45:29","2019-02-10","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Scattered rust spots all over the main mast noticed","Hull & Tanks","General Appearance","Equipment Related,External Factors",11.3,"Medium","Not Applicable","Not Applicable","To spot derust and paint","2019-04-10",null,"Completed","2019-04-29","No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T20:48:30","2019-03-10","Deficiency","Ship Staff","Ship Staff Insp.","Spare SCBA Bottles 2 Nos. Leaking,","LSA / FFA","LSA / FFA Appliances","Equipment Related",5.43,"High","Not Applicable","Not Applicable","RO for repair pars raised","2019-04-10","DEDE190095","Completed","2019-04-21","No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T20:51:05","2019-02-10","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Acommodation block Stairway (outside) landing point on deck/doubler supports rusted","Accommodation ","General Appearance","Equipment Related,External Factors",11.8,"Low","Not Applicable","Not Applicable","To derust/paint","2019-05-10",null,"Completed","2019-05-20","No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T20:55:06","2019-05-15","Deficiency","Ship Staff","Ship Staff Insp.","Bridge wing stbd side RPM indicator is not working.","Nav & comm. equip.","Navigation","Equipment Related",4.7,"High","Not Applicable","Not Applicable","Requisition made for the same","2019-06-15","DED190077","Completed","2019-06-04","No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T20:58:33","2019-05-24","Deficiency","Ship Staff","Ship Staff Insp.","Lifting handles of bunker manholes got wasted","Deck Pipe / Fittings","General Appearance","Equipment Related,External Factors",2.16,"Medium","Not Applicable","Not Applicable","Maintenance in progress","2019-06-15",null,"Completed","2019-06-08","No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T21:02:01","2019-06-12","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","All cups/spoons, empty drinking water bottle lying dirty on tables","Accommodation ","General Appearance","Behaviour Based,Human Error",11.13,"Low","Not Applicable","Not Applicable","To maintain dining saloon and recreation room neat and tidy always","2019-06-12",null,"Completed","2019-06-12","No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T21:04:53","2019-06-12","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Meat, cut vegetables kept open in Fridge","Accommodation ","General Appearance","Behaviour Based,Human Error,Inappropriate Procedure",11.13,"Low","Not Applicable","Not Applicable","To follow hygeine guidlines","2019-06-12",null,"Completed","2019-06-12","No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T21:08:26","2019-06-12","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","All natural vents (SIP) on the accomm block, louveres isolated rust/weep marks","Deck Pipe / Fittings","General Appearance","Equipment Related,External Factors",5.0999999999999996,"High","Not Applicable","Not Applicable","To derust ,paint, ,door packing  channels to derust ,packing to renew","2019-07-12",null,"Completed","2019-06-25","No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T21:13:10","2019-06-12","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Noticed lot of Valve seat rings lying loose","Miscellaneous","General Appearance","Behaviour Based,Human Error,Inappropriate Procedure",11.13,"Low","Not Applicable","Not Applicable","To indentify and prepare inventory of valve seat rings and update in PAL","2019-07-02",null,"Completed","2019-06-20","No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T21:17:26","2019-06-12","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Light fittings in around accommodation block - brackets, angle plates rusted/weep marks","Deck Pipe / Fittings","General Appearance","Equipment Related,External Factors",11.1,"Medium","Not Applicable","Not Applicable","To derust,paint and ensure regular maintenance are carried out on same","2019-07-03",null,"Completed","2019-06-26","No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T21:20:35","2019-05-20","Deficiency","Ship Staff","Ship Staff Insp.","AFT Air horn body wasted at various locations","Nav & comm. equip.","Navigation","Equipment Related,External Factors",4.7,"High","Not Applicable","Not Applicable","Replaced with new spare air horn","2019-06-15","DEDE190136","Completed","2019-06-25","No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T21:23:22","2019-06-12","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Staircase entry door in sunken deck, door locking mechanism defective","Accommodation ","Structural Condn. / WT integrity ","Equipment Related",5.0999999999999996,"High","Not Applicable","Not Applicable","To replace the lock mechanism","2019-06-27",null,"Completed","2019-06-15","No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T21:27:02","2019-06-12","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Port Windlass Gear case sump oil sight glass painted over","Mooring Mach.","General Appearance","Human Error,Knowledge Based",9.14,"Medium","Not Applicable","Not Applicable","To clean and ensure proper oil level","2019-06-19",null,"Completed","2019-06-20","No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T21:30:48","2019-01-12","Deficiency","Ship Staff","Ship Staff Insp.","Most of mooring wich hydaulic brake cylinder system for tightning and releasing brake isn ot working","Mooring Mach.","Mooring","Equipment Related",9.14,"Medium","Not Applicable","Not Applicable","Problem not found in cylinder but observed in pumping block of mooring winches, Overhauling of Block in progress.","2019-07-30","DEDE195029","Completed","2019-06-20","No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T22:14:48","2019-02-10","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","The anti fouling coat on hull damage on the stbd side at 16 mtrs draft level","Hull & Tanks","Structural Condn. / WT integrity ","Equipment Related,External Factors",11.1,"High","Not Applicable","Not Applicable","To regularly monitor the damage and report if any propagation in the coating araea .Postponed to DD and added to REFMAN","2019-12-10",null,"Completed","2019-07-07","Yes",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T22:19:21","2019-02-10","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Hull paint , Coating mechanical damage-steel exposed","Hull & Tanks","Structural Condn. / WT integrity ","Equipment Related,External Factors",11.1,"High","Not Applicable","Not Applicable","At Port & Stbd side at various location there were mechanical damages at spot coating failure, to plan to touch up at suitable anchorage.Added to REFMAN for DD.","2019-12-10",null,"Completed","2019-07-07","Yes",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T22:22:49","2019-06-12","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Gangway Port side foundation area, support plates corroded and wasted","Deck Pipe / Fittings","General Appearance","Equipment Related,External Factors",5.47,"Medium","Not Applicable","Not Applicable","Included in REFMAN for permanent repairs at DD","2019-07-19",null,"Completed","2019-07-07","Yes",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T22:26:06","2019-06-12","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Deck cross over cable supports wasted and rusted at few locations","Deck Pipe / Fittings","General Appearance","Equipment Related,External Factors",11.5,"Medium","Not Applicable","Not Applicable","Included in REFAMN for permanent repairs at DD","2019-07-19",null,"Completed","2019-07-07","Yes",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T22:30:22","2019-06-12","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Marpol drain line near port manifold , has soft patch","Deck Pipe / Fittings","Structural Condn. / WT integrity ","Equipment Related,External Factors",11.4,"Very High","Not Applicable","Not Applicable","Temporary repairs carried out.Included in REFFMAN for permanent repairs in DD.","2019-07-10",null,"Completed","2019-07-07","Yes",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T22:34:50","2019-06-12","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Stbd Windlass reported slight wobble while in operation","Mooring Mach.","Mooring","Equipment Related",9.1999999999999993,"Medium","Not Applicable","Not Applicable","Included in REFMAN for DD","2019-07-10",null,"Completed","2019-07-07","Yes",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T22:38:32","2019-06-12","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Rust weepings at underside of pipe supports observed at various sections","Deck Pipe / Fittings","General Appearance","Equipment Related,External Factors",11.5,"Medium","Not Applicable","Not Applicable","If this is not attempted soonest, the whole undersides would  get wasted in no time./FW wash carried out on weekly basis","2019-07-30",null,"Completed","2019-07-07","No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T22:43:31","2019-06-16","Critical Equipment","Ship Staff","Ship Staff Insp.","Starboard lifeboat battery defective","LSA / FFA","LSA / FFA Appliances","Equipment Related",5.29,"High","Not Applicable","Not Applicable","Both batteries replaced with spare new batteries received on 28th July 2019","2019-07-31","DEDE190149","Completed","2019-07-30","No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T22:47:31","2019-06-12","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Cable trays along with pipe stack, has an anchor point for expansion, which found the bolts painted over and seized","Deck Pipe / Fittings","General Appearance","Human Error,Inappropriate Procedure,Knowledge Based",11.5,"Medium","Not Applicable","Not Applicable","To free the bolts nad ensure they are greased and free to move","2019-07-27",null,"Completed","2019-07-30","No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T22:52:56","2019-08-25","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","No. 3 Stbd cargo oil tank IG pressure in CCR and local pressure gauge reading had a difference of 90 mm of water gauge. (3S COT sensor in CCR read 490 mm where as local pressure gauge read 400 mm of H2O). ","Inert Gas","Cargo / Ballast Systems","Equipment Related",8.19,"High","Not Applicable","Not Applicable","Sensor was replaced with new spare and difference in reading rectified","2019-09-15",null,"Completed","2019-09-03","No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T22:57:41","2019-08-08","Deficiency","Ship Staff","Ship Staff Insp.","S-Band scanner motor drive gear box gears badly damaged and also scanner driven gear 4 nos gear teeth broken","Nav & comm. equip.","Navigation","Equipment Related",4.7,"High","Not Applicable","Not Applicable","Scanner gear box renewed with new spare receive at San  Diego by the technician attended","2019-08-22",null,"Completed","2019-08-22","No",null,null,"Internal"]
[null,null,null,null,null,"2019-10-10T23:00:22","2019-08-12","Deficiency","Owner / Marine / Tech. Suptd.","Ship Staff Insp.","BA set one of the demand valve was not holding","LSA / FFA","LSA / FFA Appliances","Equipment Related",5.43,"High","Not Applicable","Not Applicable","Completed","2019-08-22","DEDE190188","Completed","2019-08-22","No",null,null,"Internal"]
[null,null,null,null,null,"2019-11-10T00:30:13","2019-09-30","Observation","Ship Staff","Ship Staff Insp.","Small section of anchor wash pipe was found holed in forward bosun store.","Miscellaneous","General Appearance","Equipment Related",9.1999999999999993,"Medium","Not Applicable","Not Applicable","Pipe repaired and fixed back.","2019-10-04",null,"Completed","2019-10-03","No",null,null,"Internal"]
[null,null,null,null,null,"13/10/2019 11:53:27 AM","2019-01-04","Observation","Ship Staff","Ship Staff Insp.","Sludge tank outlet QCV valve defective","Miscellaneous","Eng. / Strg. Comp.","Equipment Related",10.16,"Very High","Not Applicable","Not Applicable","Removed and repaired","2019-03-04",null,"Completed","2019-01-10","No",null,null,"Internal"]
[null,null,null,null,null,"13/10/2019 11:57:02 AM","2019-01-04","Observation","Ship Staff","Ship Staff Insp.","Emergency cooling valve to L.T. cooler handle broken","ER Pipes, valves & fittings","Eng. / Strg. Comp.","Equipment Related",10.29,"Medium","Not Applicable","Not Applicable","Fabricated handle and job planned","2019-03-04",null,"Completed","2019-01-10","No",null,null,"Internal"]
[null,null,null,null,null,"13/10/2019 12:00:45 PM","2019-01-05","Observation","Ship Staff","Ship Staff Insp.","#2 main cooling S.W/ pump seal leaking","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",10.29,"Medium","Not Applicable","Not Applicable","Pump overhauled","2019-01-10",null,"Completed","2019-01-09","No",null,null,"Internal"]
[null,null,null,null,null,"13/10/2019 12:03:02 PM","2019-01-05","Observation","Ship Staff","Ship Staff Insp.","Leak on S.W. outlet pipe from L.O. cooler on aft mooring hydraulics ","ER Pipes, valves & fittings","Eng. / Strg. Comp.","Equipment Related",10.31,"Very High","Not Applicable","Not Applicable","made new section of pipe","2019-01-12",null,"Completed","2019-01-11","No",null,null,"Internal"]
[null,null,null,null,null,"13/10/2019 12:06:08 PM","2019-01-06","Observation","Ship Staff","Ship Staff Insp.","S.W. outlet valve on aft L.T. cooler stuck in closed position","ER Pipes, valves & fittings","Eng. / Strg. Comp.","Equipment Related",10.31,"Very High","Not Applicable","Not Applicable","Remove and renew valve","2019-01-14",null,"Completed","2019-01-12","No",null,null,"Internal"]
[null,null,null,null,null,"13/10/2019 12:10:09 PM","2019-01-11","Observation","Ship Staff","Ship Staff Insp.","Potential leak on S.W. inlet pipe on L.O. cooler on aft mooring hydraulics ","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",10.31,"Very High","Not Applicable","Not Applicable","Section renewed","2019-01-24",null,"Completed","2019-01-11","No",null,null,"Internal"]
[null,null,null,null,null,"13/10/2019 12:13:42 PM","2019-01-12","Observation","Ship Staff","Ship Staff Insp.","F.O. overflow tank heating steam leak x 2","ER Pipes, valves & fittings","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","Steam leak rectified","2019-06-30",null,"Completed","2019-07-05","No",null,null,"Internal"]
[null,null,null,null,null,"13/10/2019 12:18:09 PM","2019-01-13","Observation","Ship Staff","Ship Staff Insp.","#1 L.O. purifier feed pump seal leaking and excessive vibration","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",10.29,"Medium","Not Applicable","Not Applicable","Pump overhaul","2019-01-30",null,"Completed","2019-01-14","No",null,null,"Internal"]
[null,null,null,null,null,"13/10/2019 12:20:53 PM","2019-01-30","Observation","Ship Staff","Ship Staff Insp.","ME FO circulating pump no 2 , mechanical seal started leaking   after c/o to LSMGO","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",10.29,"Medium","Not Applicable","Not Applicable","Pump overhauled","2019-02-05",null,"Completed","2019-02-04","No",null,null,"Internal"]
[null,null,null,null,null,"13/10/2019 12:23:55 PM","2019-02-10","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Observed continuously steaming from Vent on deck (Cascade Tank ) – wasting water/ chemical dosage","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",2.14,"Low","Not Applicable","Not Applicable","cascade temperature reduced","2019-02-17",null,"Completed","2019-02-11","No",null,null,"Internal"]
[null,null,null,null,null,"13/10/2019 12:27:08 PM","2019-02-02","Observation","Ship Staff","Ship Staff Insp.","#2 FO Purifier not de-sludging","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",10.199999999999999,"High","Not Applicable","Not Applicable","purifier bowl cleaning","2019-02-04",null,"Completed","2019-02-05","No",null,null,"Internal"]
[null,null,null,null,null,"13/10/2019 12:29:39 PM","2019-02-10","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","ME Alpha lubricator ,Noticed additional blower kept near the motor for cooling","Main Engine ","Eng. / Strg. Comp.","Equipment Related",2.14,"Low","Not Applicable","Not Applicable","Blower removed, working satisfactory","2019-02-12",null,"Completed","2019-02-12","No",null,null,"Internal"]
[null,null,null,null,null,"13/10/2019 12:33:34 PM","2019-02-10","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Fuel valve testing room Space was dirty with spilled diesel, dirty rags lying all over","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",10.19,"Very High","Not Applicable","Not Applicable","space cleaned","2019-02-17",null,"Completed","2019-02-13","No",null,null,"Internal"]
[null,null,null,null,null,"13/10/2019 3:47:32 PM","2019-02-10","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Both boiler gauge glass cock remote operating wires found seized – no indication of being operated recently","Boiler","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","Cocks eased up and lubricated wires greased","2019-02-17",null,"Completed","2019-02-14","No",null,null,"Internal"]
[null,null,null,null,null,"13/10/2019 3:51:09 PM","2019-02-10","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Port Boiler Gauge glass level - Observed diff in level between 2 adjacent gauge glass – the outboard gauge glass cock was not in fully shut condition (to drain), hard to operate","Boiler","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","Guage glass blown level corrected","2019-02-17",null,"Completed","2019-02-14","No",null,null,"Internal"]
[null,null,null,null,null,"13/10/2019 3:57:11 PM","2019-02-10","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","AHU casing rust marks on the top edges, where probably moisture/wet air was leaking","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",11.13,"Low","Not Applicable","Not Applicable","Derusted and painted","2019-02-22",null,"Completed","2019-02-17","No",null,null,"Internal"]
[null,null,null,null,null,"13/10/2019 4:00:06 PM","2019-02-10","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","AE #2 due for top overhaul","Aux. Engine","Eng. / Strg. Comp.","Equipment Related",10.119999999999999,"Very High","Not Applicable","Not Applicable","Job completed","2019-02-19",null,"Completed","2019-02-21","No",null,null,"Internal"]
[null,null,null,null,null,"13/10/2019 4:02:03 PM","2019-02-10","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Frosting observed in Fish room evaporator","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",11.13,"Low","Not Applicable","Not Applicable","working normally","2019-02-17",null,"Completed","2019-02-25","No",null,null,"Internal"]
[null,null,null,null,null,"13/10/2019 4:05:43 PM","2019-02-10","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","AC fresh air intake metal Grill found rusted and getting wasted ","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",11.13,"Low","Not Applicable","Not Applicable","Removed the Grill, blasted/derusted, painted and installed back","2019-03-10",null,"Completed","2019-03-07","No",null,null,"Internal"]
[null,null,null,null,null,"13/10/2019 4:11:43 PM","2019-02-10","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Observed slight vibration on AE #2","Aux. Engine","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","requisition raised for resilent mountings","2019-03-30",null,"Completed","2019-04-26","No",null,null,"Internal"]
[null,null,null,null,null,"13/10/2019 4:16:21 PM","2019-02-10","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Both Steering gear control motor seals leaking – dabba kept below for leakage","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",10.29,"Medium","Not Applicable","Not Applicable","Minor seal leak, will order the seals , as found no spare onboard and will plan either during sailing, either during next DD. Job added in REFFMAM","2019-12-30",null,"Completed","2019-05-23","No",null,null,"Internal"]
[null,null,null,null,null,"13/10/2019 4:22:04 PM","2019-04-28","Observation","Ship Staff","Ship Staff Insp.","Umbrella seals under #3 & #4 units leaking","Main Engine ","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","s","2019-12-10",null,"Completed","2019-12-10","No",null,null,"Internal"]
[null,null,null,null,null,"13/10/2019 4:27:25 PM","2019-05-10","Observation","Ship Staff","Ship Staff Insp.","Emergency generator radiator expansion tank water pipe connection leak","Critical Equip.","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable"," Leaking pipe welded and expansion tank refitted back;  ordered new radiator complete with expansion tank, as the existing one is in use since vessel delivery","2019-12-10",null,"Completed","2019-05-19","No",null,null,"Internal"]
[null,null,null,null,null,"13/10/2019 4:34:25 PM","2019-05-12","Observation","Ship Staff","Ship Staff Insp.","The rudder carrier greasing pump defective","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",10.29,"Medium","Not Applicable","Not Applicable","to order spares new pump","2019-06-30",null,"Completed","2019-06-04","No",null,null,"Internal"]
[null,null,null,null,null,"13/10/2019 4:38:27 PM","2019-05-15","Observation","Ship Staff","Ship Staff Insp.","Aft LT cooler SW IN valve passing","ER Pipes, valves & fittings","Eng. / Strg. Comp.","Equipment Related",10.31,"Very High","Not Applicable","Not Applicable","valve replaced with new one","2019-06-30",null,"Completed","2019-07-02","No",null,null,"Internal"]
[null,null,null,null,null,"13/10/2019 4:41:47 PM","2019-06-12","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Noticed set temp at 82 Deg C & purifier running at 78 DegC ","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",10.5,"Low","Not Applicable","Not Applicable","To always maintain temp close to 85 Dge C (as per Lukoil recommendation)","2019-06-12",null,"Completed","2019-06-12","No",null,null,"Internal"]
[null,null,null,null,null,"13/10/2019 4:45:48 PM","2019-06-12","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Observed water collected in the floor of Emergency Generator room","Miscellaneous","Eng. / Strg. Comp.","Equipment Related",11.6,"Medium","Not Applicable","Not Applicable","To check, if water tight door is leaking (while raining) or through shore cable access hole","2019-06-19",null,"Completed","2019-06-22","No",null,null,"Internal"]
[null,null,null,null,null,"13/10/2019 4:50:07 PM","2019-06-12","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","1 set of Hot plate reported defective","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related",11.13,"Low","Not Applicable","Not Applicable","defectrive hot plate repaired and rectified fault","2019-07-12",null,"Completed","2019-06-14","No",null,null,"Internal"]
[null,null,null,null,null,"13/10/2019 4:58:16 PM","2019-06-12","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","#1 AHU fresh air damper handle loose, looks disconnected from the damper mechanism","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",11.13,"Low","Not Applicable","Not Applicable","Damper fixed eased up and made operative","2019-06-27",null,"Completed","2019-06-15","No",null,null,"Internal"]
[null,null,null,null,null,"13/10/2019 5:01:27 PM","2019-06-12","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","No.1 Main FO circ pump seal leaking","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",10.29,"Medium","Not Applicable","Not Applicable","Seal and coupling with spider found damaged, same renewed with new spare. No job for coupling inspection in PAL","2019-06-27",null,"Completed","2019-06-12","No",null,null,"Internal"]
[null,null,null,null,null,"13/10/2019 5:08:31 PM","2019-06-12","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Noticed both AC Compressor running, when ambient temp was only 27 Deg C","Air Comp.","Eng. / Strg. Comp.","Equipment Related",2.14,"Low","Not Applicable","Not Applicable","Presently #2 AC compressor is running with comfortable air temperature in the accomodation. Requisition raised for overhaul of #1 AC compressor.","2019-07-12",null,"Completed","2019-06-14","No",null,null,"Internal"]
[null,null,null,null,null,"13/10/2019 5:11:39 PM","2019-06-12","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","emcy generator defective ACB to replace","Critical Equip.","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","ACB freed for its movement of cam, linkages and spindles and made operational","2019-07-12",null,"Completed","2019-07-05","No",null,null,"Internal"]
[null,null,null,null,null,"13/10/2019 5:15:34 PM","2019-06-12","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","AE 3 LO cons high 50 litres/day","Aux. Engine","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","TC cartridge for AE #3 replaced. Head decarb carried out, #1 liner replaced due to heavy scoring on AE #3.","2019-07-30",null,"Completed","2019-07-24","No",null,null,"Internal"]
[null,null,null,null,null,"13/10/2019 5:17:38 PM","2019-06-12","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Oil max pump found not running","Aux. Engine","Eng. / Strg. Comp.","Equipment Related",10.29,"Medium","Not Applicable","Not Applicable","Spare received and fixed. Pump is operational","2019-08-15",null,"Completed","2019-08-06","No",null,null,"Internal"]
[null,null,null,null,null,"13/10/2019 5:20:19 PM","2019-06-12","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Boiler water circ pump reported inlet valve leaking","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",10.29,"Medium","Not Applicable","Not Applicable","Spare recieved. valve replaced with new one","2019-09-30",null,"Completed","2019-09-06","No",null,null,"Internal"]
[null,null,null,null,null,"13/10/2019 5:23:18 PM","2019-07-13","Observation","Ship Staff","Ship Staff Insp.","emcy generator battery defective","Critical Equip.","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","Both batteries replaced with new spare battery received on 28th July 2019","2019-07-31",null,"Completed","2019-07-30","No",null,null,"Internal"]
[null,null,null,null,null,"13/10/2019 5:26:06 PM","2019-07-02","Observation","Ship Staff","Ship Staff Insp.","Aft LT cooler SW outlet valve leaking. Also suspect valve is opening partly","Critical Equip.,ER Pipes, valves & fittings","Eng. / Strg. Comp.","Equipment Related",10.31,"Very High","Not Applicable","Not Applicable","valve repalced with new one","2019-07-30",null,"Completed","2019-09-04","No",null,null,"Internal"]
[null,null,null,null,null,"13/10/2019 5:28:47 PM","2019-09-25","Observation","Ship Staff","Ship Staff Insp.","Boiler blowdown ship side valve stuck in open position","ER Pipes, valves & fittings","Eng. / Strg. Comp.","Equipment Related",10.31,"Very High","Not Applicable","Not Applicable","Valve to be replaced. Defect raised in REFFMAN","2019-10-07",null,"Completed","2019-10-07","No",null,null,"Internal"]
[null,null,null,null,null,"13/10/2019 5:43:17 PM","2019-02-10","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Main Bus Bar Circit breaker holding latches were found worn during service at Singapore","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","Job added in REFMAN as adviced by superintendent.","2019-12-10",null,"Completed","2019-03-27","No",null,null,"Internal"]
[null,null,null,null,null,"13/10/2019 5:46:00 PM","2019-02-25","Observation","Ship Staff","Ship Staff Insp.","Not able to remove anodes on outlet water box","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",10.29,"Medium","Not Applicable","Not Applicable","Anode diameter (in place was 180 mm) bigger than access hole size  in water box, removed water box and installed anodes by reducing the diameter of anodes  to 150mm as stated in the manual.","2019-03-05",null,"Completed","2019-03-01","No",null,null,"Internal"]
[null,null,null,null,null,"13/10/2019 5:48:16 PM","2019-03-27","Observation","Ship Staff","Ship Staff Insp.","Flue gas elbow to IGS  scrubber venturi tube heavily corroded","Inert Gas","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","Elbow pipe to be landed ashore next call Fujairah as sample for the fabrication of new pipe with acid resistant qualities material","2019-04-05",null,"Completed","2019-04-12","No",null,null,"Internal"]
[null,null,null,null,null,"13/10/2019 5:50:42 PM","2019-06-12","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Electrical items stored in sunken deck common stores, along with other miscellaneous items","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related",10.29,"Medium","Not Applicable","Not Applicable","To store all items – bulbs/fitting – only in Electrical or Engine stores","2019-07-03",null,"Completed","2019-06-20","No",null,null,"Internal"]
[null,null,null,null,null,"14/10/2019 8:34:14 AM","2019-02-10","Observation","Ship Staff","Ship Staff Insp.","Pipe stack anchor points for expansion – bolts seized and painted over","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",11.5,"Medium","Not Applicable","Not Applicable","Freed up","2019-02-17",null,"Completed","2019-03-07","No",null,null,"Internal"]

{"sheet":"Calc","index":2,"n_rows":28,"n_cols":12,"rows_kept":28,"cut":false,"hidden":true,"merged":[]}
["Def_type","Def_cause","Equipments","VIQrefno","Observer_code"]
[]
[]
[]
[]
[null,null,null,null,null,null,null,null,null,null,null,"Dim itemSele As Long"]
[null,null,null,null,null,null,null,null,null,null,null,"   dim startRow as integer"]
[null,null,null,null,null,null,null,null,null,null,null,"   startRow=1"]
[null,null,null,null,null,null,null,null,null,null,null,"        For itemSele = 0 To ListBox1.ListCount - 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        If ListBox1.Selected(itemSele) = True Then"]
[null,null,null,null,null,null,null,null,null,null,null,"        Worksheets(\"WorksheetName\").Range(\"A\" & startRow).Value = ListBox1.List(itemSele)"]
[null,null,null,null,null,null,null,null,null,null,null,"        startRow = startRow + 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next"]
[null,null,null,null,null,null,null,null,null,null,null,"Dim LastRowA As String"]
[null,null,null,null,null,null,null,null,null,null,null,"        Dim itemSele As Long"]
[null,null,null,null,null,null,null,null,null,null,null,"       Dim startRow as integer"]
[null,null,null,null,null,null,null,null,null,null,null,"        LastRowA = ActiveSheet.Cells(Rows.count, \"A\").End(xlUp).row"]
[null,null,null,null,null,null,null,null,null,null,null,"        startQue = 0"]
[null,null,null,null,null,null,null,null,null,null,null,"        For itemSele = 0 To ListBox1.ListCount - 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        For startRow = 1 To LastRowA"]
[null,null,null,null,null,null,null,null,null,null,null,"        If Worksheets(\"WorksheetName\").Range(\"A\" & startRow).Value = ListBox1.List(itemSele) Then"]
[null,null,null,null,null,null,null,null,null,null,null,"        ListBox1.Selected(itemSele) = True"]
[null,null,null,null,null,null,null,null,null,null,null,"        Exit For"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next j"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]

{"sheet":"Areaofobs","index":3,"n_rows":17,"n_cols":2,"rows_kept":17,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Cargo / Ballast Systems",11]
["Cert. & Docu.",2]
["Communication",6]
["Crew Management",3]
["Emgcy. Systems",13]
["Eng. / Strg. Comp.",14]
["General Appearance",15]
["Ice Opns.",17]
["LSA / FFA Appliances",8]
["MLC Related",4]
["Mooring",12]
["Navigation",5]
["MARPOL Related",9]
["ISM Related",7]
["ISPS Related",10]
["Structural Condn. / WT integrity ",16]

{"sheet":"Vessel_type","index":4,"n_rows":1,"n_cols":2,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["Vessel_type","ID"]

{"sheet":"Deficiency_type","index":5,"n_rows":9,"n_cols":3,"rows_kept":9,"cut":false,"hidden":true,"merged":[]}
["TITLE","Type of deficiency_description","ID"]
["Breakdown",null,6]
["Condn of Class / Memo",null,5]
["Critical Equipment",null,4]
["Deficiency",null,1]
["Guarantee Claim",null,8]
["Non Conformity",null,2]
["Observation",null,3]
["Other",null,7]

{"sheet":"VIQrefno","index":6,"n_rows":427,"n_cols":3,"rows_kept":427,"cut":false,"hidden":true,"merged":[]}
["VIQ_ref_no","Risk Value of observation","ID"]
["1.1","Low",8243]
["1.10","Low",8252]
["1.11","Low",8253]
["1.12","Low",8254]
["1.13","Low",8255]
["1.14","Low",8256]
["1.15","Low",8257]
["1.16","Low",8259]
["1.17","Low",8260]
["1.18","Low",8261]
["1.19","Low",8262]
["1.2","Low",8244]
["1.20","Low",8263]
["1.21","Low",8265]
["1.22","Low",8266]
["1.23","Low",8267]
["1.24","Low",8268]
["1.25","Low",8269]
["1.26","Low",8270]
["1.3","Low",8245]
["1.4","Low",8246]
["1.5","Low",8247]
["1.6","Low",8248]
["1.7","Low",8249]
["1.8","Low",8250]
["1.9","Low",8251]
["1.99","High",11258]
["10.1","Medium",8461]
["10.10","High",8470]
["10.11","Medium",8471]
["10.12","Very High",8472]
["10.13","Very High",8473]
["10.14","Medium",8474]
["10.15","Low",8475]
["10.16","Very High",8476]
["10.17","Very High",8477]
["10.18","High",8478]
["10.19","Very High",8479]
["10.2","Low",8462]
["10.20","High",8480]
["10.21","Medium",8481]
["10.22","Low",8482]
["10.23","Medium",8483]
["10.24","Low",8484]
["10.25","Very High",8485]
["10.26","High",8486]
["10.27","Medium",8487]
["10.28","Low",8488]
["10.29","Medium",8489]
["10.3","Medium",8463]
["10.30","High",8490]
["10.31","Very High",8491]
["10.32","Very High",8492]
["10.33","High",8493]
["10.34","High",8494]
["10.35","Very High",8495]
["10.36","Very High",8496]
["10.37","Medium",8497]
["10.38","Medium",8498]
["10.39","High",8499]
["10.4","High",8464]
["10.40","Medium",8500]
["10.41","Medium",8501]
["10.42","Medium",8502]
["10.43","Medium",8503]
["10.44","Medium",8504]
["10.45","Very High",8505]
["10.46","High",8506]
["10.47","Medium",8507]
["10.48","High",8508]
["10.49","Medium",8509]
["10.5","Low",8465]
["10.50","High",8510]
["10.51","Low",8511]
["10.52","Medium",8512]
["10.53","Medium",8513]
["10.54","High",8514]
["10.55","Low",8515]
["10.6","Very High",8466]
["10.7","Medium",8467]
["10.8","Medium",8468]
["10.9","Medium",8469]
["10.99","High",8516]
["11.1","High",8420]
["11.10","Medium",8429]
["11.11","Very High",8430]
["11.12","Low",8431]
["11.13","Low",8432]
["11.14","Medium",8433]
["11.15","Low",8434]
["11.16","Low",8435]
["11.17","Low",8436]
["11.2","Medium",8421]
["11.3","Medium",8422]
["11.4","Very High",8423]
["11.5","Medium",8424]
["11.6","Medium",8425]
["11.7","High",8426]
["11.8","Low",8427]
["11.9","Low",8428]
["11.99","High",8437]
["12.1","High",8438]
["12.10","High",8448]
["12.11","High",8449]
["12.12","High",8450]
["12.13","High",8451]
["12.14","High",8452]
["12.15","High",8453]
["12.16","High",8454]
["12.17","High",8455]
["12.18","High",8456]
["12.19","High",8457]
["12.2","High",8439]
["12.20","High",8458]
["12.21","High",8459]
["12.3","High",8441]
["12.4","High",8442]
["12.5","High",8443]
["12.6","High",8444]
["12.7","High",8445]
["12.8","High",8446]
["12.9","High",8447]
["12.99","High",8460]
["2.1","Very High",8296]
["2.1.9","Very High",11259]
["2.10","Medium",8304]
["2.11","Medium",8305]
["2.12","Low",8306]
["2.13","Low",8307]
["2.14","Low",8308]
["2.15","Low",8309]
["2.16","Medium",8310]
["2.2","Medium",8297]
["2.3","High",8295]
["2.4","Medium",8298]
["2.5","Medium",8299]
["2.6","Low",8300]
["2.7","High",8301]
["2.8","High",8302]
["2.9","Medium",8303]
["2.99","High",8311]
["3.1","High",8312]
["3.2","Very High",8313]
["3.3","High",8314]
["3.4","Low",8294]
["3.5","Medium",8315]
["3.6","High",8316]
["3.7","Very High",8317]
["3.8","Very High",8318]
["3.99","High",8319]
["4.1","High",8320]
["4.10","High",8329]
["4.11","Medium",8330]
["4.12","Very High",8331]
["4.13","Very High",8332]
["4.14","Very High",8333]
["4.15","Very High",8334]
["4.16","Very High",8335]
["4.17","Very High",8336]
["4.18","Very High",8337]
["4.19","Low",8338]
["4.2","Medium",8321]
["4.20","Very High",8339]
["4.21","High",8340]
["4.22","Low",8341]
["4.23","High",8342]
["4.24","High",8343]
["4.25","Low",8344]
["4.26","Low",8345]
["4.27","High",8346]
["4.3","Medium",8322]
["4.4","High",8323]
["4.5","Very High",8324]
["4.6","Medium",8325]
["4.7","High",8326]
["4.8","Medium",8327]
["4.9","Medium",8328]
["4.99","High",8347]
["5.1","Very High",8517]
["5.10","High",8526]
["5.11","Low",8527]
["5.12","Medium",8528]
["5.13","High",8529]
["5.14","Very High",8530]
["5.15","Medium",8531]
["5.16","Very High",8532]
["5.17","Very High",8533]
["5.18","High",8534]
["5.19","Medium",8535]
["5.2","Very High",8518]
["5.20","Medium",8536]
["5.21","Medium",8537]
["5.22","High",8539]
["5.23","Very High",8540]
["5.24","Very High",8541]
["5.25","Medium",8542]
["5.26","Medium",8543]
["5.27","Medium",8544]
["5.28","Very High",8545]
["5.29","High",8546]
["5.3","Low",8519]
["5.30","High",8547]
["5.31","High",8548]
["5.32","High",8549]
["5.33","High",8550]
["5.34","Low",8551]
["5.35","Medium",8552]
["5.36","Low",8553]
["5.37","Low",8554]
["5.38","High",8555]
["5.39","Very High",8556]
["5.4","High",8520]
["5.40","Very High",8557]
["5.41","Very High",8558]
["5.42","Medium",8559]
["5.43","High",8560]
["5.44","High",8561]
["5.45","Medium",8564]
["5.46","Medium",8565]
["5.47","Medium",8566]
["5.48","Medium",8567]
["5.5","Low",8521]
["5.6","Low",8522]
["5.7","Medium",8523]
["5.8","Medium",8524]
["5.9","Very High",8525]
["5.99","High",8568]
["6.1","Medium",8348]
["6.10","Low",8357]
["6.11","High",8358]
["6.12","Medium",8359]
["6.13","Low",8360]
["6.14","High",8361]
["6.15","High",8362]
["6.16","Very High",8363]
["6.17","Very High",8364]
["6.18","Medium",8365]
["6.19","Low",8366]
["6.2","High",8349]
["6.20","Medium",8367]
["6.21","High",8368]
["6.22","Medium",8369]
["6.3","Low",8350]
["6.4","High",8351]
["6.5","Medium",8352]
["6.6","Medium",8353]
["6.7","High",8354]
["6.8","High",8355]
["6.9","Low",8356]
["6.99","High",8370]
["7.1","High",8371]
["7.10","High",8380]
["7.11","High",8381]
["7.12","High",8382]
["7.13","Medium",8383]
["7.14","Medium",8384]
["7.15","High",8385]
["7.16","High",8386]
["7.17","High",8387]
["7.2","High",8372]
["7.3","Low",8373]
["7.4","Low",8374]
["7.5","Low",8375]
["7.6","Medium",8376]
["7.7","Low",8377]
["7.8","High",8378]
["7.9","High",8379]
["7.99","High",8388]
["8.1","Very High",8569]
["8.10","Very High",8578]
["8.100","Low",11227]
["8.101","Medium",11228]
["8.102","Low",11229]
["8.103","Low",11230]
["8.104","Low",11231]
["8.105","Medium",11232]
["8.106","Medium",11233]
["8.107","Low",11234]
["8.108","High",11235]
["8.109","Very High",11236]
["8.11","Medium",8579]
["8.110","High",11237]
["8.111","Medium",11238]
["8.112","High",11239]
["8.113","Medium",11240]
["8.114","Low",11241]
["8.115","High",11242]
["8.116","Medium",11243]
["8.117","Medium",11244]
["8.118","Medium",11245]
["8.119","High",11246]
["8.12","Medium",8580]
["8.120","High",11247]
["8.121","Medium",11248]
["8.122","High",11249]
["8.123","High",11250]
["8.124","Low",11251]
["8.125","High",11252]
["8.126","Medium",11253]
["8.127","Medium",11254]
["8.13","Medium",8581]
["8.14","Very High",8582]
["8.15","High",8583]
["8.16","Very High",8584]
["8.17","Low",8585]
["8.18","High",8586]
["8.19","High",8587]
["8.199","High",11255]
["8.2","Medium",8570]
["8.20","Medium",8588]
["8.21","High",8589]
["8.22","Very High",8590]
["8.23","Medium",8591]
["8.24","Medium",8592]
["8.25","Very High",8593]
["8.26","High",8594]
["8.27","Medium",8595]
["8.28","Medium",8596]
["8.29","High",8598]
["8.3","Very High",8571]
["8.30","High",8599]
["8.31","High",8600]
["8.32","Low",8601]
["8.33","Medium",8602]
["8.34","High",8603]
["8.35","Medium",8604]
["8.36","Medium",8605]
["8.37","High",8607]
["8.38","Medium",8608]
["8.39","Medium",8609]
["8.4","Medium",8572]
["8.40","High",8610]
["8.41","Medium",8611]
["8.42","Medium",8612]
["8.43","Very High",8613]
["8.44","High",8615]
["8.45","High",8616]
["8.46","Very High",8617]
["8.47","Very High",8618]
["8.48","Medium",8619]
["8.49","High",8620]
["8.5","Very High",8573]
["8.50","Medium",8621]
["8.51","Low",8622]
["8.52","Low",8623]
["8.53","Low",8624]
["8.54","High",8625]
["8.55","Low",11182]
["8.56","Medium",11183]
["8.57","Medium",11184]
["8.58","High",11185]
["8.59","High",11186]
["8.6","Medium",8574]
["8.60","High",11187]
["8.61","Medium",11188]
["8.62","Very High",11189]
["8.63","High",11190]
["8.64","Medium",11191]
["8.65","Low",11192]
["8.66","High",11193]
["8.67","High",11194]
["8.68","High",11195]
["8.69","Medium",11196]
["8.7","High",8575]
["8.70","Medium",11197]
["8.71","Very High",11198]
["8.72","Medium",11199]
["8.73","Medium",11200]
["8.74","High",11201]
["8.75","Medium",11202]
["8.76","Medium",11203]
["8.77","Medium",11204]
["8.78","Medium",11205]
["8.79","Medium",11206]
["8.8","Medium",8576]
["8.80","Medium",11207]
["8.81","Low",11208]
["8.82","Medium",11209]
["8.83","Low",11210]
["8.84","Low",11211]
["8.85","Medium",11212]
["8.86","Medium",11213]
["8.87","Medium",11214]
["8.88","Low",11215]
["8.89","High",11216]
["8.9","High",8577]
["8.90","High",11217]
["8.91","High",11218]
["8.92","Medium",11219]
["8.93","Low",11220]
["8.94","Low",11221]
["8.95","Medium",11222]
["8.96","Medium",11223]
["8.97","Low",11224]
["8.98","High",11225]
["8.99","Medium",11226]
["9.1","Low",8390]
["9.10","Medium",8399]
["9.11","Medium",8400]
["9.12","Medium",8401]
["9.13","Low",8402]
["9.14","Medium",8403]
["9.15","Medium",8404]
["9.16","High",8405]
["9.17","High",8406]
["9.18","Low",8407]
["9.19","Low",8408]
["9.2","Very High",8391]
["9.20","Medium",8409]
["9.21","Medium",8410]
["9.22","Low",8411]
["9.23","Low",8412]
["9.24","Medium",8413]
["9.25","Low",8414]
["9.26","Low",8415]
["9.27","Low",8416]
["9.28","Medium",8417]
["9.29","Low",8418]
["9.3","Very High",8392]
["9.4","High",8393]
["9.5","High",8394]
["9.6","Low",8395]
["9.7","Medium",8396]
["9.8","Medium",8397]
["9.9","Medium",8398]
["9.99","High",8419]

{"sheet":"Equipment_list","index":7,"n_rows":21,"n_cols":3,"rows_kept":21,"cut":false,"hidden":true,"merged":[]}
["TITLE","Equipment_list_description","ID"]
["Accommodation ",null,12]
["Air Comp.",null,8]
["Aux. Engine",null,4]
["Aux. Mach.",null,7]
["Boiler",null,5]
["Cargo Mach.",null,13]
["Critical Equip.",null,16]
["Deck Mach.",null,18]
["Deck Pipe / Fittings",null,20]
["Documentation",null,21]
["Elect. Mach. & Equip.",null,10]
["Hull & Tanks",null,19]
["Inert Gas",null,14]
["LSA / FFA",null,17]
["Main Engine ",null,3]
["Miscellaneous",null,22]
["Nav & comm. equip.",null,11]
["ER Pipes, valves & fittings",null,9]
["Purifier",null,6]
["Mooring Mach.",null,15]

{"sheet":"PSC_MOU","index":8,"n_rows":11,"n_cols":3,"rows_kept":11,"cut":false,"hidden":true,"merged":[]}
["TITLE","PSC_MOU_description","ID"]
["Asia and the Pacific",null,2]
["Caribbean",null,4]
["Europe and the North Atlantic",null,1]
["Latin America",null,3]
["The Black Sea region",null,6]
["The Indian Ocean",null,8]
["The Mediterranean",null,7]
["The Riyadh MoU",null,9]
["USCG",null,10]
["West and Central Africa",null,5]

{"sheet":"Inspection_type","index":9,"n_rows":15,"n_cols":2,"rows_kept":15,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Bunkering Audit",14]
["Others (Eg. Insurance etc.)",12]
["Flag State Insp.",5]
["Ship Staff Insp.",15]
["IT Audit",10]
["OM Insp. (Eg. SIRE, CDI etc.)",6]
["ISM Audit",2]
["ISPS Audit",3]
["MLC Audit",1]
["Mooring Audit",9]
["Nav Audit / Verification",8]
["PSC Inspection",4]
["Suptd. Insp.",13]
["Terminal Insp.",11]

{"sheet":"Deficiency_Cause","index":10,"n_rows":8,"n_cols":3,"rows_kept":8,"cut":false,"hidden":true,"merged":[]}
["TITLE","Deficiency_Cause_description","ID"]
["Behaviour Based",null,1]
["Equipment Related",null,4]
["External Factors",null,5]
["Human Error",null,7]
["Inappropriate Procedure",null,8]
["Industry Issue",null,6]
["Knowledge Based",null,3]

{"sheet":"Observer_code","index":11,"n_rows":9,"n_cols":3,"rows_kept":9,"cut":false,"hidden":true,"merged":[]}
["TITLE","Observer_code_description","ID"]
["Class Surveyor",null,4]
["Others (Eg. Insurance etc.)",null,9]
["FSC Inspector",null,5]
["Owner / Marine / Tech. Suptd.",null,3]
["PSC Insp.",null,6]
["Ship Staff",null,2]
["SIRE / CDI Insp.",null,8]
["Terminal Insp.",null,7]

{"sheet":"Status_code","index":12,"n_rows":6,"n_cols":3,"rows_kept":6,"cut":false,"hidden":true,"merged":[]}
["TITLE","Status_code_description","ID"]
["Completed",null,6]
["Deferred to D D",null,5]
["In progress",null,3]
["Not Started",null,2]
["Waiting spare",null,4]

{"sheet":"PSC_ref_no","index":13,"n_rows":19,"n_cols":2,"rows_kept":19,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Alarms",9]
["Cargo operations including equipment",7]
["Certificates & Documentation",2]
["Dangerous Goods",13]
["Emergency Systems",5]
["Fire safety",8]
["ISM",16]
["ISPS",17]
["Life saving appliances",12]
["MLC, 2006",18]
["Other",19]
["Pollution Prevention",15]
["Propulsion and auxiliary machinery",14]
["Radio communication",6]
["Safety of Navigation",11]
["Structural condition",3]
["Water/Weathertight condition",4]
["Working and Living Conditions",10]

{"sheet":"Risk_value_of_obs","index":14,"n_rows":1,"n_cols":2,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["Risk Value of observation","ID"]

{"sheet":"Year","index":15,"n_rows":18,"n_cols":1,"rows_kept":18,"cut":false,"hidden":true,"merged":[]}
["Year"]
[2014]
[2015]
[2016]
[2017]
[2018]
[2019]
[2020]
[2021]
[2022]
[2023]
[2024]
[2025]
[2026]
[2027]
[2028]
[2029]
[2030]

{"sheet":"Month","index":16,"n_rows":13,"n_cols":1,"rows_kept":13,"cut":false,"hidden":true,"merged":[]}
["Month"]
["Jan"]
["Feb"]
["Mar"]
["Apr"]
["May"]
["Jun"]
["Jul"]
["Aug"]
["Sep"]
["Oct"]
["Nov"]
["Dec"]

{"sheet":"Date_","index":17,"n_rows":32,"n_cols":1,"rows_kept":32,"cut":false,"hidden":true,"merged":[]}
["Date"]
["01"]
["02"]
["03"]
["04"]
["05"]
["06"]
["07"]
["08"]
["09"]
[10]
[11]
[12]
[13]
[14]
[15]
[16]
[17]
[18]
[19]
[20]
[21]
[22]
[23]
[24]
[25]
[26]
[27]
[28]
[29]
[30]
[31]

{"sheet":"Sheet1","index":18,"n_rows":24,"n_cols":6,"rows_kept":24,"cut":false,"hidden":true,"merged":[]}
[]
[null,"ID","E",null,"Date Recorded",1]
[null,"UNIQUE ID","F",null,"Type of Deficiency",2]
[1,"Date Recorded","G",null,"Observer code",3]
["ignore","Vessel Type","H",null,"Type of Inspection",4]
[null,"Internal / External","I",null,"Description of Deficiency",5]
[null,"Drydock","J",null,"Equipment Categories",6]
[null,"Information Sharing","K",null,"Area of Observation",7]
[null,"Critical_item","L",null,"Deficiency Cause",8]
[null,"Deficiency Type","M",null,"VIQ Ref Number",9]
[null,"Deficiency Cause","N",null,"Risk Value of Obs",10]
[null,"Inspection Type","O",null,"PSC Ref Number",11]
[null,"Equipments","P",null,"PSC MOU ID",12]
[null,"VIQ Reference Number","Q",null,"Action Taken or Required",13]
[null,"Risk Value of the observation","R",null,"Target Date",14]
[null,"PSC Reference Number","S",null,"PO Ref No.",15]
[null,"PSC MOU","T",null,"Status Code",16]
[null,"Observer Code","U",null,"Date Completed",17]
[null,"Target Date","V",null,"Drydock",18]
[null,"Status Code","W",null,"Info Sharing",19]
[null,"Description of Deficiency","X",null,"Critical Item Flag",20]
[null,"Action taken / required","Y",null,"Audit Type",21]
[null,"PO ref no","Z"]
[null,"Date completed","AA"]

{"sheet":"Ship_information","index":19,"n_rows":2,"n_cols":3,"rows_kept":2,"cut":false,"hidden":true,"merged":[]}
["Ship_ID","Ship_Name","FILE_NAME"]
["25","DHT EDELWEISS","25_1570626119692.xlsm"]