{"text_format":"1","workbook":"xlsx","n_sheets":24,"sheets":["Mainsheet","Completed","Calc","Areaofobs","Vessel_type","Deficiency_type","VIQrefno","Equipment_list","PSC_MOU","Inspection_type","Deficiency_Cause","Observer_code","Status_code","PSC_ref_no","Risk_value_of_obs","Year","Month","Date_","Sheet1","Ship_information","External_Deficiency_type","External_Inspection_type","External_Observer_code","Sheet Version"],"not_rendered":{"charts":0,"images":6,"macros":1,"external_links":0,"defined_names":12,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Mainsheet","index":0,"n_rows":63,"n_cols":28,"rows_kept":63,"cut":false,"hidden":false,"merged":[[10,8,10,9],[10,12,10,13],[12,6,12,27],[8,6,8,27]]}
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,"Defect - Damage Monitoring Sheet"]
[]
[null,null,null,null,null,null,null,"Date of Report","2020-01-15",null,null,"Ship Name","APHRODITE (20-01-2020)"]
[]
[null,null,null,null,null,null,"VERSION : 2.0"]
[]
[]
[]
[null,null,null,null,"ID","UNIQUE ID","Date Recorded","Type of Deficiency","Observer code","Type of Inspection","Description of Deficiency","Equipment Categories","Area of Observation","Deficiency Cause","VIQ Ref Number","Risk Value of Obs","PSC Ref Number","PSC MOU ID","Action Taken or Required","Target Date","PO Ref No.","Status Code","Date Completed","Drydock","Info Sharing","Critical Item","Audit Type","Superintendent Remarks"]
[null,null,null,null,6348,"91_Sat May 11 2019 00:20:12 GMT+0000 (Coordinated Universal Time)","2019-10-27","Defect","Ship Staff","Ship Staff Insp.","AE 3 governor top cover stop solenoid inoperational","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","General and trip alarm is being generated but engine is not stopping in any condiiton. Governor top cover connector is faulty and this is not giving STOP signal for the engine to stop. Office has raised PO from there end. Awaiting spares.","2020-02-15","APHR195048","Waiting spare",null,"No","No","No","Internal","Based on VFF, the order is awaiting readiness advice from supplier. As this is a very high risk value observation, will push procurement to obtain readiness status."]
[null,null,null,null,6350,"91_Tue Nov 05 2019 01:21:01 GMT+0000 (Coordinated Universal Time)","2019-10-27","Defect","Ship Staff","Ship Staff Insp.","Main Engine FO backwash filter not operational","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","After opeing filter found, Filter distributor not turning as same is jammed in the housing. New spare ordered.","2020-03-01","APHR190011","Waiting spare",null,"No","No","No","Internal","Based on VFF, the order is currently awaiting readiness advice."]
[null,null,null,null,6354,"91_Wed Sep 11 2019 15:20:11 GMT+0000 (Coordinated Universal Time)","2019-10-27","Defect","Ship Staff","Ship Staff Insp.","Poop deck, widespread spot rusting","Hull & Tanks","General Appearance","Inappropriate Procedure","","","","","Derusting and painting to be planned--40% Completed","2020-01-30","","In progress",null,"No","No","No","Internal","Basis status code indicating \"In progress\", pls revert with updated status of job progress based on percentage basis."]
[null,null,null,null,6355,"91_Wed Sep 11 2019 15:24:50 GMT+0000 (Coordinated Universal Time)","2019-10-27","Defect","Ship Staff","Ship Staff Insp.","Mooring winches and bases have heavy rusting","Deck - Machinery","General Appearance","Equipment Related","","","","","Derusting and painting to be planned--Aft mooring winches 15% Job completed","2020-01-30","","In progress",null,"No","No","No","Internal","Basis status code indicating \"In progress\", pls revert with updated status of job progress based on percentage basis."]
[null,null,null,null,6356,"91_Wed Sep 11 2019 15:27:44 GMT+0000 (Coordinated Universal Time)","2019-10-27","Defect","Ship Staff","Ship Staff Insp.","Widespread rusting on pipe supports on main deck","Deck - Pipe / Fittings","General Appearance","Equipment Related","","","","","Derusting and painting to be planned","2020-01-31","","In progress",null,"No","No","No","Internal","Basis status code indicating \"In progress\", pls revert with updated status of job progress based on percentage basis."]
[null,null,null,null,6358,"91_Wed Sep 11 2019 15:42:18 GMT+0000 (Coordinated Universal Time)","2019-10-29","Observation","Ship Staff","Ship Staff Insp.","No eyewash available on deck area","Miscellaneous","ISM Related","Equipment Related",null,null,"Not Applicable","Not Applicable","Request new eye wash with shower","2020-01-31",null,"Waiting spare",null,"No","No","No","Internal","Vessel has yet to issue RO for supply of new eye wash system."]
[null,null,null,null,6368,"91_Sun Nov 10 2019 01:08:16 GMT+0000 (Coordinated Universal Time)","2019-10-27","Defect","Ship Staff","Ship Staff Insp.","Provision Compressor CSW pump no 2 found noisy","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","PO raised awaiting spares","2020-02-01","APHR200042","Waiting spare",null,"No","No","No","Internal","When do you plan to carry out the overhaul? Do you have sufficient spare parts on board for pump overhauling?"]
[null,null,null,null,6369,"91_Sun Nov 10 2019 01:05:33 GMT+0000 (Coordinated Universal Time)","2019-10-27","Defect","Ship Staff","Ship Staff Insp.","IG Scrubber cooling pump suction line from sea chest found having a hole. Temporary repairs has been carried out at present","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.31","Very High","","","Ship staff will revert back with all the dimensions and drawing for the same.","2021-01-31","","Deferred to D D",null,"Yes","No","No","Internal","Noted. Basis risk value indicated as very high, when do you plan to carry out line renewal. What is the length of suction line requiring renewal? Pls forward photograph of the affect line to this office for our review."]
[null,null,null,null,6370,"91_Fri Oct 11 2019 01:09:55 GMT+0000 (Coordinated Universal Time)","2019-10-27","Defect","Ship Staff","Ship Staff Insp.","ER workshop AC no 2 not operational","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","vessel has raised PO for new package air condition for workshop","2020-03-01",null,"Waiting spare",null,"No","No","No","Internal","Technical Supt. pls advice on renewal plans."]
[null,null,null,null,6371,"91_Sun Nov 10 2019 01:11:24 GMT+0000 (Coordinated Universal Time)","2019-10-27","Defect","Ship Staff","Ship Staff Insp.","Ships Elevator not operational","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","vessel has raised service request for elevator at next convient port","2020-02-29","APHR200023","Waiting spare",null,"No","No","No","Internal","Tech Supt. pls advice when you plan to arange service the elevator."]
[null,null,null,null,6372,"91_Sun Nov 10 2019 01:13:50 GMT+0000 (Coordinated Universal Time)","2019-10-27","Defect","Ship Staff","Ship Staff Insp.","ME Fwd TC RPM meter not functional","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","PO for same to be raised in 2020.","2020-03-01",null,"Waiting spare",null,"No","No","No","Internal","We are yet to receive your RO# for same. Presume you plan to issue same in Jan 2020  Pls advice."]
[null,null,null,null,6373,"91_Mon Nov 11 2019 17:36:10 GMT+0000 (Coordinated Universal Time)","2019-10-27","Defect","Ship Staff","Ship Staff Insp.","ME Viscotherm not operational","Miscellaneous","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","Trouble shooting in progress.","2020-02-15",null,"In progress",null,"No","No","No","Internal","Pls revert with outcome of your trouble shooting for same?"]
[null,null,null,null,6374,"91_Mon Nov 11 2019 03:07:07 GMT+0000 (Coordinated Universal Time)","2019-10-27","Defect","Ship Staff","Nav Audit / Verification","ECDIS Units used to hanged during normal operation, frequency is daily, not available for navigation once ECDIS hangs,  have to restart the ECDIS to bring it back to normal","Navigation - ECDIS","Navigation","Equipment Related","4.7","High","","","ECDIS units has to restart every time it hangs/ freezes.-->As per Elec Suptd,Old Memory Deleted from the system,Under Observation now","2020-01-30","","In progress",null,"No","No","No","Internal","Mr. Kamlesh to advice vessel on same. Capt. pls revert with outcome of your observation."]
[null,null,null,null,6375,"91_Mon Nov 11 2019 03:26:41 GMT+0000 (Coordinated Universal Time)","2019-10-27","Defect","Ship Staff","Ship Staff Insp.","AIO Overlay is not available in ECDIS. NAVTEX Overlay not available in ECDIS. RADAR Overlay is not available in ECDIS. Wind Data is not available in ECDIS. Log Speed/ STW is not available in ECDIS.","Navigation - ECDIS","Navigation","Equipment Related","4.7","High","","","For AIO and NAVTEX Overlay: v/l is plotting T & P notices and NAVTEX warnings on user maps.","2020-01-31","","Not Started",null,"No","No","No","Internal","Mr. Kamlesh to advice vessel on same."]
[null,null,null,null,6376,"91_Wed Dec 11 2019 01:51:05 GMT+0000 (Coordinated Universal Time)","2019-10-27","Defect","Ship Staff","Ship Staff Insp.","MF/HF DSC Controller does not have a Printer. Also the Display LCD backlight of MF/HF Controller unit is not working due to which the Data is unreadable.","Navigation - GMDSS & Communication","Navigation","Equipment Related","4.23","High","","","PO raised for Printer. PO Numbe: APHR 195034 (ex APHR190021)","2020-01-31","APHR 195034 (ex APHR190021)","Not Started",null,"No","No","No","Internal","Mr. Kamlesh to advice vessel on same.\nRO#APHR190021 - Based on VFF this RO is still in the processing stage."]
[null,null,null,null,6377,"91_Tue Nov 12 2019 02:00:36 GMT+0000 (Coordinated Universal Time)","2019-10-27","Defect","Ship Staff","Ship Staff Insp.","Display unit of S-Band Radar not stable/ happened once/ starts flickering and screen becomes red/ the data is totally unreadable. Also the scanner unit makes loud noise once it starts operation and it goes away with the rotation of scanner.","Navigation - RADAR","Navigation","Equipment Related",4.7,"High","Not Applicable","Not Applicable","Have to restart the system then only the error rectify. Pesently moniotring the situation and will troubleshoot as per required.","2020-01-31",null,"Not Started",null,"No","No","No","Internal","Mr. Kamlesh to advice vessel on same."]
[null,null,null,null,6378,"91_Wed Dec 11 2019 02:11:36 GMT+0000 (Coordinated Universal Time)","2019-10-27","Defect","Ship Staff","Ship Staff Insp.","Fluid level in Spare Magnetic Compass Bowl is very low/ Compass Bowl is Almost 30% empty.","Navigation - Others","Navigation","Equipment Related",4.7,"High","Not Applicable","Not Applicable","PO Raised for Magnetic Compass Bowl Fluid/ will refill on receiving.","2020-01-31","APHR 195034 (APHR190021)","Not Started",null,"No","No","No","Internal","Mr. Kamlesh to advice vessel on same.  Based on VFF, RO#APHR195034 is in processing stage."]
[null,null,null,null,6382,"91_19/11/2019 7:07:11 PM","2019-10-27","Defect","Ship Staff","Ship Staff Insp.","AE Viscotherm not operational","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","Trouble shooting in progress.","2020-02-28",null,"In progress",null,"No","No","No","Internal","Pls revert with update on status of trouble shooting of the unit & revert with your findings. Target date to be amended due to same already overdue."]
[null,null,null,null,6383,"91_19/11/2019 7:19:25 PM","2019-10-27","Defect,Defect","Ship Staff","Ship Staff Insp.","ME Flowmeter not readable. all numbers have faded and very dificult to take readings.","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","For the moment numbers marked with paint marker, new RO raised for same.Communication is that owners might go for a new digital type FM. Awaiting further instruction.","2020-03-01","APHR195015 (ex APHR190007)","Waiting spare",null,"No","No","No","Internal","Based on VFF, the RO is currently in processing stage. Technical Superintendent to advice with regards to supplying vessel with a new digital type FM."]
[null,null,null,null,6386,"91_19/11/2019 7:26:51 PM","2019-10-27","Defect","Ship Staff","Ship Staff Insp.","AE 3 due for decarbonisation","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Awaiting spares and office confirmation.","2020-03-31","APHR190010","Waiting spare",null,"No","No","No","Internal","Based on VFF, RO is closed and will be re-issued in year 2020.\nThus please re-issue a new RO for the requested parts."]
[null,null,null,null,6400,"91_20/11/2019 1:41:21 AM","2019-11-15","Defect","Ship Staff","Ship Staff Insp.","Baking Oven in galley showing low insulation","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","10.38","Medium","","","New baking oven to be ordered next budget year.","2020-02-29","","Not Started",null,"No","No","No","Internal","Understand RO for supply of new oven will be submitted in January 2020."]
[null,null,null,null,6401,"91_20/11/2019 1:46:19 AM","2019-11-15","Defect","Ship Staff","Ship Staff Insp.","All 3 Auxiliary Engines FO change over switch to DO not operational. Same has to be done my manually opening the 3 way valve in local side","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","At present operation carried out manually. Trouble shooting in progress.","2020-02-28","","In progress",null,"No","No","No","Internal","Pls update progress of your trouble shooting and revert with your findings?"]
[null,null,null,null,6403,"91_20/11/2019 1:58:17 AM","2019-11-15","Defect","Ship Staff","Ship Staff Insp.","IG Chiller plant not operational","Cargo Mach.","Cargo / Ballast Systems","Equipment Related",8.5,"Medium","Not Applicable","Not Applicable","vessel has opened up compressor for overhauling will revert back with detailed troubleshooting.","2020-02-28",null,"In progress",null,"No","No","No","Internal","Pls update status of your progress in trouble shooting of the unit  and on possible cause of the problem. Pls issue RO for parts required for overhauling of the compressor."]
[null,null,null,null,6405,"91_20/11/2019 2:15:56 AM","2019-10-30","Defect","Ship Staff","Ship Staff Insp.","LT and HT system for ME and AE chloride content very high. SW leakage in to the system.","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","Regular draining of both M.E and A.E L.T water on daily basis, chloride level came down to 150ppm","2020-02-28",null,"In progress",null,"No","No","No","Internal","Based on your action taken to date, no leakage noted at both coolers & expansion tank. Pls check other possibilites where SW could leak into the system & revert."]
[null,null,null,null,6406,"91_20/11/2019 7:51:29 PM","2019-10-15","Defect","Ship Staff","Ship Staff Insp.","Heavy rusting on cargo lines non insulated areas near manifold and cross over valves","Deck - Pipe / Fittings","Cargo / Ballast Systems","Inappropriate Procedure","10.32","Very High","","","Coating prepartion and protection to be carried out.","2020-02-28","","Not Started",null,"No","No","No","Internal","When do you plan to commence de-rusting and coating of the lines?"]
[null,null,null,null,6407,"91_20/11/2019 4:00:36 AM","2019-10-27","Defect","Ship Staff","Ship Staff Insp.","Boiler chloride level very very high","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","Regular bottom blow down of boiler are being carried out, chloride level came down to 200 ppm.","2020-02-28",null,"In progress",null,"No","No","No","Internal","Basis your advice that chloride level hs come down, pls verify same & if all is well this defect can be closed out."]
[null,null,null,null,6415,"91_20/11/2019 5:14:07 AM","2019-10-30","Defect","Ship Staff","Ship Staff Insp.","ME local maneuvering platform mechanical RPM meter showing difference of 10 RPM. RPM counter also not working.","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","Spare RPM meter to be ordered","2020-03-31",null,"Not Started",null,"No","No","No","Internal","At ME stop position, does the RPM meter indicate \"0\" or \"10\" RPM. Is there any knob on the meter where the error can be adjusted? Otherwise, pls issue & submit RO for supply of new meter."]
[null,null,null,null,6416,"91_20/11/2019 5:15:50 AM","2019-10-24","Defect","Ship Staff","Ship Staff Insp.","ME Rpm hunting when at Dead Slow and slow in AHD as well as Astern direction","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Trouble shooting carried out and office reported about the same. Emergency Stop Solenoid valve (MV-ES 404) is not getting energised and therefore the Directional Control Valve is not supplying air to the Stop Air cylinder (002) and the engine is not stopping.","2020-02-28","","In progress",null,"No","No","No","Internal","Pls revert with update on trouble shooting of the problem."]
[null,null,null,null,6429,"91_20/11/2019 8:06:18 AM","2019-10-27","Critical Equipment","Ship Staff","Ship Staff Insp.","S Band Radar making noise when it starts","Navigation - RADAR","Navigation","Equipment Related","","","","","Under observation. Trouble shooting in progress.","2019-12-31","","In progress",null,"No","No","No","Internal","Pls revert with outcome of your trouble shooting / observation."]
[null,null,null,null,6430,"91_20/11/2019 8:16:12 AM","2019-10-27","Defect","Ship Staff","Ship Staff Insp.","Both Main Air Compressors taking very long time to build up pressure. Performance is not good.","E/R - Air Comp.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","vessel has raised PO'S for the same awating spares.","2020-02-28","APHR190016","Waiting spare",null,"No","No","No","Internal","Based on VFF, the spares should have been ready for delivery on 23rd December 2019. Procurement to check with supplier on same."]
[null,null,null,null,6431,"91_20/11/2019 8:17:56 AM","2019-11-15","Defect","Ship Staff","Ship Staff Insp.","Break wire alarm for AE 2 not working","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","PLC new ordered.","2020-03-31","APHR200005","Waiting spare",null,"No","No","No","Internal","Pls revert with progress update on your trouble shooting. Based on VFF, RO still in processing stage."]
[null,null,null,null,7300,"91_Thu Dec 12 2019 18:05:35 GMT+0000 (Coordinated Universal Time)","2019-11-25","Defect","Ship Staff","Ship Staff Insp.","ER Workshop AC no 1 compressor damaged due to malfuntion of the high pressure trip switch.","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","AS PER SHORE TECHNICIAN RECOMENDATION, WORKSHOP AC. #1 STOPPED UNTIL FURTHER INVESTIGATION FROM SHORE TECHNICIAN AT NEXT CALL  FUJAIRAH.","2020-02-28",null,"In progress",null,"No","No","No","Internal","Pls revert with update on your observation. If all is well, then you should close-out the defect."]
[null,null,null,null,7303,"91_15/12/2019 1:41:22 PM","2019-12-02","Defect","Ship Staff","Ship Staff Insp.","When pressing emergency stop button for Main Engine, it was observed that at times the fuel lever is not coming to 0 and engine is hunting at slow RPM.","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","VESSEL HAS RAISED REQ FOR COMPLETE NABCO REMOTE CONTROL SERVICE AND GOVERNOR SERVICE AT SUITABLE PORT CALL.","2020-03-15","APHR200020, APHR200029","In progress",null,"No","No","No","Internal","It has been approx. 01 month since the defect was reported. Pls revert with your findings and actions required for verification of the fault. If spares required, pls issue RO# for same."]
[null,null,null,null,7304,"91_15/12/2019 3:45:03 PM","2019-12-01","Defect,Defect","Ship Staff","Ship Staff Insp.","Refer compressor CSW pump no 1 has cold work done on the pump casing.","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","Requisition raised for complete overhaul of pump ","2020-03-31","APHR200042","Waiting spare",null,"No","No","No","Internal","Noted.  In order to avoid delay in supply of new pump casing, pls provide details of the existing pump via email so that procurement can source for the required pump casing in advance."]
[null,null,null,null,7306,"91_15/12/2019 3:48:51 PM","2019-12-05","Defect,Defect","Ship Staff","Ship Staff Insp.","Stbd side aft Outside accommodation light near aft paint store base is broken","Deck - Pipe / Fittings","Structural Condn. / WT integrity ","Behaviour Based,Equipment Related,External Factors","","","","","Base to be cropped and renewed. This requires Hotwork on Deck. To be planned accordingly.","2020-01-15","","Not Started",null,"No","No","No","Internal","When do you plan to carry out cropping & renewal of the affected base? RA & hot work permit will be required for same."]
[null,null,null,null,7307,"91_15/12/2019 3:52:37 PM","2019-12-05","Defect","Ship Staff","Ship Staff Insp.","EHQ & Hyd rm Natural vent flap & Packing very poor condition.","Deck - Pipe / Fittings","General Appearance","External Factors,Human Error",null,null,"Not Applicable","Not Applicable","COCOP & Renewal of packing to be done","2020-01-31",null,"Not Started",null,"No","No","No","Internal","When do you plan to commence renewal of the affected packing since the target date provided is already overdue? Is spare packing avaiable on board?"]
[null,null,null,null,7308,"91_15/12/2019 3:57:01 PM","2019-12-05","Defect,Defect","Ship Staff","Ship Staff Insp.","2 Nos. Ceiling board on A deck, 1 No. on B-Deck Staircase Port side are cracked.---No Spare ceiling Board Onboard","Accommodation","MLC Related","Human Error","","","","","All to be renewed","2020-01-31","","Not Started",null,"No","No","No","Internal","Pls issue RO# for supply of spare ceiling boards. Why no RO issued since date of defect recorded?"]
[null,null,null,null,7310,"91_15/12/2019 4:04:04 PM","2019-12-05","Defect","Ship Staff","Ship Staff Insp.","Cosmatic & Coating condition on Port and Stbd Manifols Area Very Poor.","Deck - Pipe / Fittings,Miscellaneous","General Appearance","Behaviour Based,External Factors","","","","","Chipping and Painting in Progress.","2020-01-15","","In progress",null,"No","No","No","Internal","Pls revert with updates on progress of the job, based on percentage basis."]
[null,null,null,null,7312,"91_15/12/2019 4:14:40 PM","2019-12-01","Defect","Ship Staff","Ship Staff Insp.","Many of Bridge IMO Publication required as per Goodwood Library are missing Since Takeover.","Navigation - Others","Navigation","Human Error,Inappropriate Procedure",null,null,"Not Applicable","Not Applicable","To be Supplied by office/Navtor.--->Reminders Sent to Office","2020-01-31",null,"In progress",null,"No","No","No","Internal","We recomended that you prepare an updated list of the missing publications and forward same to this office (relevant dept) for supply of same. Was this done? If yes, to whom was the list sent?"]
[null,null,null,null,7317,"91_15/12/2019 4:31:51 PM","2019-12-11","Defect","Ship Staff","Ship Staff Insp.","Transmitter boxes for cargo system on deck needs to be chipped carefully and painted and cleaned.","Cargo Mach.,Miscellaneous","General Appearance","Behaviour Based,Human Error,Inappropriate Procedure,Knowledge Based",null,null,"Not Applicable","Not Applicable","All to be opened and carry out the job carefully.","2020-01-31",null,"In progress",null,"No","No","No","Internal","Pls revert with updated status on job progress to date & amend target date as necessary."]
[null,null,null,null,7319,"91_15/12/2019 4:39:19 PM","2019-12-11","Defect","Ship Staff","Ship Staff Insp.","IMO symbols at various location are in dull condition.","Miscellaneous","General Appearance","Behaviour Based,External Factors",null,null,"Not Applicable","Not Applicable","Needs to be replaced with new one.--->RO Raised","2020-01-31",null,"In progress",null,"No","No","No","Internal","Understand replacement of the IMO symbols is in progress. Pls revert with updated status for same & provide revised target date."]
[null,null,null,null,7320,"91_15/12/2019 4:43:03 PM","2019-11-30","Defect,Defect","Ship Staff","Nav Audit / Verification","Sextant onboard is in broken condition.","Navigation - Others","Navigation","Behaviour Based,Equipment Related,Human Error",null,null,"Not Applicable","Not Applicable","Needs to be replaced with new one.--->RO Raised","2020-01-31",null,"Not Started",null,"No","No","No","Internal","Pls submit RO# for supply of new sextant in Jan 2020."]
[null,null,null,null,9283,"91_22/12/2019 11:33:35 PM","2019-12-15","Defect","Ship Staff","Ship Staff Insp.","AHU duct above AC compressor no 1 found to be damaged during routine inspection.","Miscellaneous","General Appearance","Equipment Related,Inappropriate Procedure","10.32","Very High","","","Duct to be repaired.","2020-12-01","","Deferred to D D",null,"Yes","No","No","Internal","Technical Superintendent to advice."]
[null,null,null,null,9350,"91_1/1/2020 9:19:43 PM","2019-12-30","Defect","Ship Staff","Ship Staff Insp.","Both Hot water calorifier heater element showing low insulation.","Miscellaneous","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","vessel has raised P.O ","2020-02-28","APHR200002","Waiting spare",null,"No","No","No","Internal","Pls issue RO for the required parts & submit via PAL system. Ensure all details & specs. are correctly indicated in RO in order to supply correct parts."]
[null,null,null,null,9351,"91_1/1/2020 11:13:42 PM","2019-11-21","","Ship Staff","Ship Staff Insp.","Speed shown by Doppler Log is not accurate","Navigation - Echo Sounder / Speed Log","Navigation","Equipment Related,External Factors","","","","","Needs troubleshoot","2020-02-28","","Not Started",null,"No","No","No","Internal","Pls revert with update on your trouble-shooting & findings."]
[null,null,null,null,null,"91_3/1/2020 8:00:04 PM","2019-12-26","Defect","Ship Staff","Ship Staff Insp.","Fixed gas detector for accomodation officer smoke room and upper deck entrance port side not working","Accommodation","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","PO raised for the spares","2020-02-01","APHR200046","Waiting spare",null,"No",null,null,"Internal"]

{"sheet":"Completed","index":1,"n_rows":124,"n_cols":28,"rows_kept":124,"cut":false,"hidden":false,"merged":[[10,8,10,9],[10,12,10,13],[12,6,12,27],[8,6,8,27]]}
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,"Defect - Damage Monitoring Sheet"]
[]
[null,null,null,null,null,null,null,"Date of Report","2-0-2020",null,null,"Ship Name","APHRODITE (02-01-2020)"]
[]
[null,null,null,null,null,null,"VERSION : 2.0"]
[]
[]
[]
[null,null,null,null,"ID","UNIQUE ID","Date Recorded","Type of Deficiency","Observer code","Type of Inspection","Description of Deficiency","Equipment Categories","Area of Observation","Deficiency Cause","VIQ Ref Number","Risk Value of Obs","PSC Ref Number","PSC MOU ID","Action Taken or Required","Target Date","PO Ref No.","Status Code","Date Completed","Drydock","Info Sharing","Critical Item","Audit Type","Superintendent Remarks"]
[null,null,null,null,6346,"91_20/11/2019 5:59:44 AM","2019-11-15","Defect","Ship Staff","Ship Staff Insp.","Cargo compressor glycol pump no 2 seized","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","","","","","Pump overhauled and made operational","2019-11-20","","Completed","2019-11-15","No","No","No","Internal"]
[null,null,null,null,6347,"91_31/10/2019 3:14:24 AM","2019-10-27","Critical Equipment,Defect","Ship Staff","Ship Staff Insp.","AE 2 safety system not operational\t\t","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","All alarms and trips have been tried out. Electrical and mechanical overspeed also working fine. ","2019-11-15","","Completed","2019-11-15","No","No","No","Internal"]
[null,null,null,null,6349,"91_Tue Nov 05 2019 00:37:50 GMT+0000 (Coordinated Universal Time)","2019-10-27","Defect","Ship Staff","Ship Staff Insp.","All 3 AE's current maximum load capacity is 550 kW where as the rated generator capacity is 975 kW","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Performance for all 3 gennys taken at 700kW. Normal working load increased to 600-650kW for all generators. ","2020-02-28","","Completed","2019-12-19","No","No","No","Internal","Pls update job progress to date. Are there sufficient spare parts on board to complete remaining head overhauls."]
[null,null,null,null,6351,"91_Sat May 11 2019 01:26:56 GMT+0000 (Coordinated Universal Time)","2019-10-27","Defect","Ship Staff","Ship Staff Insp.","Aux Engine FO backwash filter not operational\t","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Made operational and turning","2019-12-31","APHR190037","Completed","2019-12-13","No","No","No","Internal"]
[null,null,null,null,6352,"91_Wed Sep 11 2019 13:48:45 GMT+0000 (Coordinated Universal Time)","2019-10-27","Defect","Ship Staff","Ship Staff Insp.","deck and paint store in poor and disorganised condition","Accommodation,Miscellaneous","General Appearance","Inappropriate Procedure","","","","","All Deck stores and Paint Stores are arranged properly.","2019-11-30","","Completed","2019-11-30","No","No","No","Internal"]
[null,null,null,null,6353,"91_Wed Sep 11 2019 13:52:39 GMT+0000 (Coordinated Universal Time)","2019-10-27","Defect","Ship Staff","Ship Staff Insp.","main deck forward of acc, widespread spot rusting","Hull & Tanks","General Appearance","Inappropriate Procedure","","","","","Main Deck Fwd of Acc to Compressor room aft Spot chipping & Painting Completed","2019-12-30","","Completed","2019-12-09","No","No","No","Internal"]
[null,null,null,null,6357,"91_Wed Sep 11 2019 15:31:23 GMT+0000 (Coordinated Universal Time)","2019-10-28","Defect","Ship Staff","Ship Staff Insp.","Provision vegetable room door lock damage","Accommodation","General Appearance","Inappropriate Procedure","","","","","Renewed.","2019-12-31","","Completed","2019-11-15","No","No","No","Internal","Is new door lock available on board? If yes, when do you plan to replace same?"]
[null,null,null,null,6359,"91_Sat Nov 09 2019 15:47:49 GMT+0000 (Coordinated Universal Time)","2019-10-29","Non Conformity","Ship Staff","Ship Staff Insp.","Emergency shower starboard side not working","Deck - Pipe / Fittings","ISM Related","Equipment Related","","","","","To be clear the pipes, request new shower","2019-12-31","","Completed","2019-12-08","No","No","No","Internal"]
[null,null,null,null,6360,"91_Sun Nov 10 2019 00:28:01 GMT+0000 (Coordinated Universal Time)","2019-10-27","Defect","Ship Staff","Ship Staff Insp.","FWG Starboard water generation is very low.\t","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","FWG plate cleaning carried out. Now generating 12 MT/ day. ","2019-12-31","","Completed","2019-11-08","No","No","No","Internal"]
[null,null,null,null,6361,"91_Fri Oct 11 2019 00:31:08 GMT+0000 (Coordinated Universal Time)","2019-10-27","Defect","Ship Staff","Ship Staff Insp.","Housekeeping in ER found to be in very poor condition. Cosmetic condition also very bad","E/R - Aux. Engine,E/R - Aux. Mach.,E/R - Boiler,E/R - Main Engine","General Appearance","Equipment Related","","","","","Work in progress. ER stores stripped of all boxes and now completely arranged. Chemical locker stripped, cleaned and painted. Upgradation work in full swing. ME all leaks rectified. AE all leaks rectified. Purifier room all leaks rectified complete cleaning carried out. Cosmetic conditon has improved considerably. Work will be carried out on daily basis.","2019-12-30","","Completed","2019-12-23","No","No","No","Internal","Basis status code indicating \"In progress\", pls revert with updated status of job progress."]
[null,null,null,null,6362,"91_Fri Oct 11 2019 00:38:17 GMT+0000 (Coordinated Universal Time)","2019-10-27","Defect","Ship Staff","Ship Staff Insp.","As per remaining Thai crew onboard, the general practice of the previous Management (BSM) was to put all ER drain water in Clean Drain tank and same was being educted overboard.","Miscellaneous","Eng. / Strg. Comp.","Inappropriate Procedure","","","","","Clean drain tank cleaned and practice stopped.","2019-11-30","","Completed","2019-11-15","No","No","No","Internal"]
[null,null,null,null,6363,"91_Sun Nov 10 2019 00:40:32 GMT+0000 (Coordinated Universal Time)","2019-10-27","Defect,Defect","Ship Staff","Ship Staff Insp.","Innumerable Fuel and LO leakages on Main Engine and Auxiliary Engine","E/R - Aux. Engine,E/R - Aux. Mach.,Elect. Mach. & Equip.,Main Engine ,Miscellaneous,E/R - Pipes/ valves & fittings,E/R - Purifier","Eng. / Strg. Comp.","Equipment Related","10.29","Medium","","","Leaks rectified on ME and AE","2019-12-30","","Completed","2019-12-14","No","No","No","Internal"]
[null,null,null,null,6364,"91_Sun Nov 10 2019 00:42:23 GMT+0000 (Coordinated Universal Time)","2019-10-27","Defect","Ship Staff","Ship Staff Insp.","Main Engine LO cooler temperature controller not operational","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Made operational now","2019-12-21","","Completed","2019-12-16","No","No","No","Internal","Pls revert with your findings during trouble shooting of the unit."]
[null,null,null,null,6365,"91_Fri Oct 11 2019 00:45:19 GMT+0000 (Coordinated Universal Time)","2019-10-27","Defect","Ship Staff","Ship Staff Insp.","ER spare room in bad condition","Miscellaneous","Eng. / Strg. Comp.","Behaviour Based","","","","","Spare room stripped, cleaned, mopped and all boxes arranged sequentially.","2019-12-15","","Completed","2019-12-10","No","No","No","Internal"]
[null,null,null,null,6366,"91_Sun Nov 10 2019 00:54:29 GMT+0000 (Coordinated Universal Time)","2019-10-27","Defect","Ship Staff","Ship Staff Insp.","Oil accumulation in all ER bilge wells","Miscellaneous","General Appearance","Behaviour Based,Equipment Related","10.29","Medium","","","All bilge wells emptied, de mucked, cleaned and fresh coat of paint applied.","2019-11-30","","Completed","2019-11-12","No","No","No","Internal"]
[null,null,null,null,6367,"91_Sun Nov 10 2019 01:02:16 GMT+0000 (Coordinated Universal Time)","2019-10-27","Defect","Ship Staff","Ship Staff Insp.","Main engine pit bilge alarm not working","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","10.3","Medium","","","Alarm working now. Rectified.","2019-11-30","","Completed","2019-11-25","No","No","No","Internal"]
[null,null,null,null,6379,"91_Wed Dec 11 2019 02:23:34 GMT+0000 (Coordinated Universal Time)","2019-10-27","Defect","Ship Staff","Ship Staff Insp.","First Aid Kits missing form its designated locations onboard.","Accommodation","Emgcy. Systems","Behaviour Based,Human Error","11.15","Low","","","PO raised for new First Aid Kits/ will replace once received.","2019-12-31","APHR 190009","Completed","2019-11-17","No","No","No","Internal"]
[null,null,null,null,6381,"91_Wed Dec 11 2019 02:34:40 GMT+0000 (Coordinated Universal Time)","2019-10-27","Defect","Ship Staff","Ship Staff Insp.","2 units of Bridge window wiper not working out of total 3 units.","Navigation - Others","Navigation","Equipment Related","11.16","Low","","","Both window wipers repaired and are working now.","2019-12-31","","Completed","2019-12-15","No","No","No","Internal","Pls advice when you plan to carry out trouble shooting and revert with your findings."]
[null,null,null,null,6385,"91_19/11/2019 7:25:21 PM","2019-10-27","Defect,Defect","Ship Staff","Ship Staff Insp.","Several air leaks found for air lines on deck and in ER.\t\t","Deck - Pipe / Fittings,E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Leaks rectified","2019-12-31","","Completed","2019-11-30","No","No","No","Internal"]
[null,null,null,null,6387,"91_19/11/2019 7:55:43 PM","2019-10-29","Defect","Ship Staff","Ship Staff Insp.","Air Lock room door alarm not working","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.4","Medium","","","Trouble shooting carried out and made operational.","2019-12-31","","Completed","2019-12-14","No","No","No","Internal"]
[null,null,null,null,6388,"91_19/11/2019 7:57:55 PM","2019-10-29","Defect","Ship Staff","Ship Staff Insp.","Cargo alarm for deck not working","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","","","","","Air horn overhauled.","2019-12-30","","Completed","2019-12-09","No","No","No","Internal"]
[null,null,null,null,6389,"91_19/11/2019 8:04:25 PM","2019-10-30","Defect","Ship Staff","Ship Staff Insp.","Gas engineer cabin alarm not working","Miscellaneous","Eng. / Strg. Comp.","Equipment Related","","","","","Made operational and tested.","2019-12-15","","Completed","2019-12-13","No","No","No","Internal","Defect was reported on 30/10/2019 and since today, it has yet to be trouble shoot. Pls advice reason for the delay."]
[null,null,null,null,6390,"91_19/11/2019 8:07:49 PM","2019-10-30","Critical Equipment,Defect","Ship Staff","Ship Staff Insp.","Emergency Cargo pump no 1 and 2 start switch getting stuck","Cargo Mach.,Elect. Mach. & Equip.","Cargo / Ballast Systems","Equipment Related","","","","","Switch repaired and made operational.","2019-12-15","","Completed","2019-12-08","No","No","No","Internal","Are spare start switches available on board? If yes, when do you plan to replace same? If no, why no RO# has been issued & submitted to this office?"]
[null,null,null,null,6391,"91_19/11/2019 8:10:12 PM","2019-10-30","Defect","Ship Staff","Ship Staff Insp.","Compressor room bilge alarm not functional","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","Alarm made operational.","2019-12-15","","Completed","2019-12-07","No","No","No","Internal","Pls advice when you plan to carry out the checks & take corrective action? It is very important that all alarms should be functioning at all times. Pls look into this matter immediately."]
[null,null,null,null,6392,"91_19/11/2019 8:16:05 PM","2019-10-30","Defect","Ship Staff","Ship Staff Insp.","Repeated failure and surging of all AE's Turbocharger observed","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","This type of problem is inherent of this series of engines as per previous recorded history. Cause has been identified and problem rectified. For last one month there has been no break down. ","2019-11-30","","Completed","2019-11-28","No","No","No","Internal"]
[null,null,null,null,6394,"91_20/11/2019 1:06:11 AM","2019-10-30","Critical Equipment","Ship Staff","Ship Staff Insp.","ER blower no 5 damper not closing properly","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Rectified and operational.","2019-12-19","","Completed","2019-12-17","No","No","No","Internal","Pls revert with updated progress status on your rectification of the defect. Basis very high risk value, you should have completed the job by now."]
[null,null,null,null,6397,"91_20/11/2019 1:24:36 AM","2019-11-15","Breakdown","Ship Staff","Ship Staff Insp.","FW pipe to funnel deck above near ER skylight is wasted","Deck - Pipe / Fittings","Eng. / Strg. Comp.","Equipment Related","","","","","New pipe fabricated and put in place.","2019-12-31","","Completed","2019-12-19","No","No","No","Internal","Noted that the job have not been started to date. Pls advice reason for same. Is replacement pipe available on board? Pls provide details of the existing pipe that needs replacing."]
[null,null,null,null,6398,"91_20/11/2019 1:28:19 AM","2019-10-30","Defect","Ship Staff","Ship Staff Insp.","HFO and LO Purifier operation water tank Inlet valves are leaking","E/R - Pipes/ valves & fittings,E/R - Purifier","Eng. / Strg. Comp.","Equipment Related","","","","","Both operating water tank valves renewed with new ones ","2020-01-31","APHR190037","Completed","2019-12-30","No","No","No","Internal","What is the current status of the valves? Based on VFF, RO is still under processing stage."]
[null,null,null,null,6399,"91_20/11/2019 1:33:20 AM","2019-10-30","Defect","Ship Staff","Ship Staff Insp.","Condition of insulation in ER is in poor condition for machineries and piping systems.","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Insulation renewed where it was found damaged","2020-03-31","","Completed","2019-12-25","No","No","No","Internal","We notice that despite indicating very high risk value of the observation, no RO has been issued for supply of insulation material to date. Pls verify delay in doing so."]
[null,null,null,null,6402,"91_20/11/2019 1:49:36 AM","2019-10-30","Defect","Ship Staff","Ship Staff Insp.","AE 2 TC outlet temperature sensor showing incorrect reading","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Sensor replaced with new spare sensor.","2019-12-30","","Completed","2019-12-15","No","No","No","Internal","Is spare sensor available on board? If yes, when do you plan to replace same? If no, why no RO has been issued for supply of the sensor?"]
[null,null,null,null,6404,"91_20/11/2019 2:13:29 AM","2018-10-30","Defect","Ship Staff","Ship Staff Insp.","LT cooler no 2 performance very poor","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","LT cooler cleaning carried out and now performance is better.","2019-12-31","","Completed","2019-11-24","No","No","No","Internal"]
[null,null,null,null,6408,"91_20/11/2019 4:06:55 AM","2019-10-27","Critical Equipment","Ship Staff","Ship Staff Insp.","OWS 15 ppm monitor calibration is due and monitor is erratic","Critical Equip.","MARPOL Related","Equipment Related","6.17","Very High","","","New OMD sensor and OWS PCB installed at FUJARAH by shore technician, 15 ppm caliberation carried out, all ship staff training carried out for the same. ","2019-12-30","APHR190015","Completed","2019-12-26","No","No","No","Internal","Based on VFF, RO currently in processing stage."]
[null,null,null,null,6409,"91_20/11/2019 4:42:15 AM","2019-11-15","Defect","Ship Staff","Ship Staff Insp.","Fire detectors in ER are not marked and identified","LSA / FFA","LSA / FFA Appliances","Equipment Related,Inappropriate Procedure","5.35","Medium","","","All fire detectors identified and marked.","2019-12-15","","Completed","2019-12-08","No","No","No","Internal","Pls revert with status on work progress to date."]
[null,null,null,null,6410,"91_20/11/2019 4:44:10 AM","2019-10-30","Defect","Ship Staff","Ship Staff Insp.","Electrical mats not in place at several location on board. ","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","10.24","Low","","","Completed.","2019-12-31","","Completed","2019-12-05","No","No","No","Internal"]
[null,null,null,null,6411,"91_20/11/2019 4:47:14 AM","2019-10-30","Critical Equipment","Ship Staff","Ship Staff Insp.","Bolts in all flanges of OWS to be sealed with numbered tags","Critical Equip.","MARPOL Related","Equipment Related","6.18","Medium","","","Seals put as per Enviromental Log","2019-12-15","","Completed","2019-12-12","No","No","No","Internal"]
[null,null,null,null,6412,"91_20/11/2019 4:54:55 AM","2019-10-30","Defect","Ship Staff","Ship Staff Insp.","EGE soot blower not working","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Nozzle found choked and pipe broken. New pipe fabricated and nozzle cleared.","2020-02-28","","Completed","2019-12-14","No","No","No","Internal"]
[null,null,null,null,6413,"91_20/11/2019 5:01:58 AM","2019-10-30","Defect","Ship Staff","Ship Staff Insp.","Boiler performance is very low. Max steam output is around 3 bars.","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Dry washing of boiler side and economiser side carried out and boiler performance has improved. Generating steam upto 4.5 kg now.","2019-12-31","","Completed","2019-12-23","No","No","No","Internal","Please advice when you plan to carry out the required action. Again you have indicated risk value of the observation as \"very high\" but to date no action taken."]
[null,null,null,null,6414,"91_20/11/2019 5:10:46 AM","2019-10-30","Defect","Ship Staff","Ship Staff Insp.","ER stores not arranged properly. Spares kept in a chaotic manner","Miscellaneous","General Appearance","Equipment Related","","","","","Stores stripped of all boxes, cleaned, mopped and boxes put back sequentially and arranged.","2019-12-31","","Completed","2019-12-10","No","No","No","Internal"]
[null,null,null,null,6417,"91_20/11/2019 5:19:03 AM","2019-10-27","Defect","Ship Staff","Ship Staff Insp.","ME Unit no 2 CW jacket leaking","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","10.29","Medium","","","Leak arrested. ","2020-02-28","","Completed","2019-11-25","No","No","No","Internal"]
[null,null,null,null,6418,"91_20/11/2019 5:21:34 AM","2019-10-27","Defect","Ship Staff","Ship Staff Insp.","Several ME crankcase door leaking","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","10.29","Medium","","","Leaks rectified.","2020-02-28","","Completed","2019-12-11","No","No","No","Internal"]
[null,null,null,null,6419,"91_20/11/2019 5:29:05 AM","2019-10-30","Defect","Ship Staff","Ship Staff Insp.","ME Fuel pump leakage from several places","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","10.29","Medium","","","No.1 injector overhauled and leaks rectified from various high pressure pipes.","2020-02-28","","Completed","2019-12-14","No","No","No","Internal","What is the current situation with the leaks?"]
[null,null,null,null,6420,"91_20/11/2019 5:38:11 AM","2019-11-15","Defect","Ship Staff","Ship Staff Insp.","Aft LO purifier leaks intermittently","E/R - Purifier","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Overhauling carried out. ","2019-12-31","","Completed","2019-11-26","No","No","No","Internal","Prior to comencing overhaul, we recommend that you check availability of the necessary spare parts on board. If not submit RO for the required parts."]
[null,null,null,null,6421,"91_20/11/2019 5:44:21 AM","2019-11-15","Defect","Ship Staff","Ship Staff Insp.","Control air compressor tripping on High temperature even after cleaning the cooler","E/R - Air Comp.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Problem rectified.","2019-12-31","","Completed","2019-12-17","No","No","No","Internal","Pls provide update on your findings during the trouble shooting process. Check piping for possible obstructions both at inlet & outlet ends of the cooler."]
[null,null,null,null,6422,"91_20/11/2019 5:51:37 AM","2019-10-30","Defect","Ship Staff","Ship Staff Insp.","All cargo compressors condensor outlet expansion valve all are in manual mode. None od them are working in Auto","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.33","High","","","All five cargo compressor expansion valve made operational in AUTO mode. ","2020-02-28","","Completed","2019-12-30","No","No","No","Internal","Pls revert with updated status on your progress with trouble shooting."]
[null,null,null,null,6423,"91_20/11/2019 6:19:17 AM","2019-10-27","Defect","Ship Staff","Ship Staff Insp.","Boiler auto mode not working.","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Boiler automation made operational.","2020-01-31","","Completed","2019-12-23","No","No","No","Internal","Please revert with findings during trouble shooting of the unit & update progress status for same."]
[null,null,null,null,6425,"91_20/11/2019 6:36:18 AM","2019-10-28","Defect","Ship Staff","Ship Staff Insp.","Condition of deck lights is bad leading to low insulation","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","10.24","Low","","","Deck lights insulation rectified. ","2020-02-28","","Completed","2019-12-20","No","No","No","Internal","Pls specify condition of the deck lights (are these damaged / faulty / rusted etc) & forward photographs of same for our review. What do you need to improve the situation?"]
[null,null,null,null,6426,"91_20/11/2019 7:57:31 AM","2019-10-27","Defect","Ship Staff","Ship Staff Insp.","Emergency Fire pump priming unit shaft seal leaking","LSA / FFA","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Leak rectified.","2020-01-31","","Completed","2019-12-10","No","No","No","Internal"]
[null,null,null,null,6427,"91_20/11/2019 8:00:29 AM","2019-11-07","Defect","Ship Staff","Ship Staff Insp.","Aft hydraulic pumps discharge pressure gauges not working","Deck - Mooring Machinery","Cargo / Ballast Systems","Equipment Related","","","","","PG renewed.","2019-12-31","","Completed","2019-12-21","No","No","No","Internal","Please advice if necessary spares / new gauges are available on board for replacement of the faulty units? If no, recommend that RO for same and any other faulty/damaged gauges to be submitted & forwarded to this office as your earliest,"]
[null,null,null,null,6428,"91_20/11/2019 8:03:09 AM","2019-10-27","Defect","Ship Staff","Ship Staff Insp.","Low tank level alarm not working on Bridge for Steering Gear ","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.39","High","","","Trouble shooting carried out and made operational.","2019-11-30","","Completed","2019-11-29","No","No","No","Internal"]
[null,null,null,null,6432,"91_Sat May 11 2019 00:49:59 GMT+0000 (Coordinated Universal Time)","2019-10-27","Breakdown","Ship Staff","Ship Staff Insp.","Starboard AC compressor not operational. No history given by previous managers\t","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Vessel attended by AC technician at Fujairah anchorage. They had borught an overhauled compressor.Same was replaced and system started.","2019-11-16","","Completed","2019-11-04","No","No","No","Internal"]
[null,null,null,null,6433,"91_Tue Nov 05 2019 01:23:36 GMT+0000 (Coordinated Universal Time)","2019-10-27","Defect","Ship Staff","Ship Staff Insp.","Main Engine LO backwash filter not operational\t","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Filter cleaning was carried out. Vessel had one spare hydraulic motor for the backwash filter, same renewed.","2019-11-15","","Completed","2019-11-02","No","No","No","Internal"]
[null,null,null,null,6434,"91_Fri Oct 11 2019 00:25:58 GMT+0000 (Coordinated Universal Time)","2019-10-27","Defect","Ship Staff","Ship Staff Insp.","Port FWG performance very poor. No water being produced\t","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","Port FWG taken out of service. Cleaning of plates carried out and put back into service.Producing around 24MT/day now.","2019-11-15","","Completed","2019-11-07","No","No","No","Internal"]
[null,null,null,null,6435,"91_Fri Oct 11 2019 00:33:57 GMT+0000 (Coordinated Universal Time)","2019-10-27","Defect","Ship Staff","Ship Staff Insp.","All Sludge tanks in ER full upto 90% at the time of takeover.\t","Miscellaneous","Eng. / Strg. Comp.","Equipment Related,Inappropriate Procedure","","","","","Deslopping of Sludge carried out at Fujairah during bunkering operation","2019-11-16","","Completed","2019-11-04","No","No","No","Internal"]
[null,null,null,null,6436,"91_19/11/2019 7:31:23 PM","2019-10-27","Defect","Ship Staff","Ship Staff Insp.","AE 3 pre-lub oil pump not starting/stopping on Auto","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Trouble shooting carried out and system made operational.","2019-11-30","","Completed","2019-11-18","No","No","No","Internal"]
[null,null,null,null,6437,"91_19/11/2019 7:34:45 PM","2019-10-27","Defect","Ship Staff","Ship Staff Insp.","220V low insulation alarm on Main Switchboard not working\t","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","10.38","Medium","","","Trouble shooting carried out and system made operational. Alarm functioning now.","2019-11-30","","Completed","2019-11-15","No","No","No","Internal"]
[null,null,null,null,6438,"91_19/11/2019 7:42:36 PM","2019-10-27","Defect","Ship Staff","Ship Staff Insp.","440V low insulation alarm on Main Switchboard not working","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","10.38","Medium","","","Trouble shooting carried out and alamr function made operation","2019-11-30","","Completed","2019-11-15","No","No","No","Internal"]
[null,null,null,null,6439,"91_19/11/2019 7:40:13 PM","2019-10-27","Defect","Ship Staff","Ship Staff Insp.","220V low insulation alarm on Emergency Switchboard not working\t","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","10.38","Medium","","","Trouble shooting carried out and alarm made operational.","2019-11-30","","Completed","2019-11-15","No","No","No","Internal"]
[null,null,null,null,6440,"91_19/11/2019 7:48:40 PM","2019-10-30","Critical Equipment","Ship Staff","Ship Staff Insp.","IS telephone in Compressor and Motor room not working","Critical Equip.","Communication","Equipment Related","","","","","Trouble shooting carried out and system made operational","2019-11-30","","Completed","2019-11-15","No","No","No","Internal"]
[null,null,null,null,6441,"91_19/11/2019 7:51:29 PM","2019-10-25","Critical Equipment","Ship Staff","Ship Staff Insp.","Several alarms for Steering Gear not operational.","E/R - Aux. Mach.,Critical Equip.","Eng. / Strg. Comp.","Equipment Related","10.39","High","","","All alarms checked as per requirement. Trouble shooting carried out and problems rectified. ","2019-10-30","","Completed","2019-10-30","No","No","No","Internal"]
[null,null,null,null,6442,"91_20/11/2019 12:13:45 AM","2019-10-30","Non Conformity","Ship Staff","Ship Staff Insp.","Electric fixed grinder installed in Deck Workshop on the Upper deck. This is hot work and should not be on deck.","Miscellaneous","LSA / FFA Appliances","Equipment Related","","","","","Power supply removed and grinder/buffing machine removed from location and shifted to ER workshop.","2019-11-07","","Completed","2019-11-05","No","No","No","Internal"]
[null,null,null,null,6443,"91_20/11/2019 1:36:16 AM","2019-10-30","Defect","Ship Staff","Ship Staff Insp.","Sewage shift pump operation not satisfactory","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Pump overhauled and put back in use","2019-11-30","","Completed","2019-11-21","No","No","No","Internal"]
[null,null,null,null,6444,"91_20/11/2019 2:12:12 AM","2019-10-30","Defect","Ship Staff","Ship Staff Insp.","LT Cooler no 1 performance very poor.","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","LT cooler needs to be cleaned","2020-02-28","","Completed","2019-11-17","No","No","No","Internal"]
[null,null,null,null,6445,"91_20/11/2019 5:34:31 AM","2019-10-27","Defect","Ship Staff","Ship Staff Insp.","ME TC Grit washing hopper choked and not in use","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","","","","","Hopper and drain pipe cleared and system put in use","2019-11-30","","Completed","2019-11-03","No","No","No","Internal"]
[null,null,null,null,6446,"91_20/11/2019 7:00:53 AM","2019-10-27","Defect","Ship Staff","Ship Staff Insp.","Sewage treatment plant side manhole door one stud found broken and therefore there is slight leak from Sewage tank","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Broken stud removed and new stud put back, leak rectified.","2020-01-31","","Completed","2019-12-21","No","No","No","Internal","Pls submit RA & Hot work permit to obtain concurrence from this office prior to commencing any repairs."]
[null,null,null,null,6447,"91_Mon Nov 11 2019 17:34:12 GMT+0000 (Coordinated Universal Time)","2019-10-27","Breakdown","Ship Staff","Ship Staff Insp.","Service Air Compressor pressure sensor found defective","E/R - Air Comp.","Eng. / Strg. Comp.","Equipment Related","","","","","Pressure sensor renewed and problem rectified","2019-11-30","APHR190001","Completed","2019-11-16","No","No","No","Internal"]
[null,null,null,null,7301,"91_14/12/2019 10:08:59 PM","2019-12-09","Breakdown","Ship Staff","Ship Staff Insp.","Main Air Compressor no 2(outbound) motor found burnt while in operation.","E/R - Air Comp.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","New motor received and same renewed and working now.","2019-12-31","APHR190043","Completed","2019-12-16","No","No","No","Internal","Understand that new motor was supplied on board on 15th Dec 2019 @ Sharjah. Pls keep this office updated once the motor has been installed & compressor in operation."]
[null,null,null,null,7305,"91_15/12/2019 3:41:01 PM","2019-12-05","Defect","Ship Staff","Ship Staff Insp.","Port side Bunker drip Tray aft drain pipe corroded and holed.","Deck - Pipe / Fittings","General Appearance","Behaviour Based,External Factors","","","","","Repaired","2020-01-31","","Completed","2019-12-21","No","No","No","Internal","Pls update as to when you plan to carry out said job."]
[null,null,null,null,7309,"91_15/12/2019 4:00:57 PM","2019-12-05","Defect","Ship Staff","Ship Staff Insp.","Glycol pump Flenge leaking","Miscellaneous","Cargo / Ballast Systems","Behaviour Based,External Factors,Human Error","","","","","Rectified.","2019-12-31","","Completed","2019-12-23","No","No","No","Internal","Is the replacement Gasket available on board? When do you plan to resolve this issue?"]
[null,null,null,null,7311,"91_15/12/2019 4:08:10 PM","2019-12-05","Defect","Ship Staff","Ship Staff Insp.","Fire isolation valves in fire station upper deck for accommodation & Engine room are tight to operate.","Critical Equip.","General Appearance","Behaviour Based,External Factors,Knowledge Based","","","","","Eased up","2019-12-31","","Completed","2019-12-20","No","No","No","Internal","These items should be given top priority and made operational soonest."]
[null,null,null,null,7313,"91_15/12/2019 4:19:17 PM","2019-12-11","Defect","Ship Staff","Ship Staff Insp.","Steam return line on main deck(S) abreast of No. 4 Cargo tank holed and leaking on deck.","Deck - Pipe / Fittings","Cargo / Ballast Systems","Behaviour Based,Equipment Related","","","","","Leak rectified","2019-12-31","","Completed","2019-12-17","No","No","No","Internal","Pls advice when you plan to carry out repairs to the leaking line? \nThis should take priority as it is dangerous to ignore a leaking steam line on deck. Have the leak been isolated temporarily? Pls forward photograph of the affected pipeline via email for our reference."]
[null,null,null,null,7314,"91_15/12/2019 4:23:13 PM","2019-12-11","Defect","Ship Staff","Ship Staff Insp.","Pressure guage in fwd on Main Fire Line is Broken and Not working.","Deck - Pipe / Fittings","LSA / FFA Appliances","Equipment Related,Knowledge Based","","","","","Renewed.","2019-12-31","","Completed","2019-12-19","No","No","No","Internal","Since vessel have not submitted RO#, we can only assume that spare pressure gauge is available on board. If so, why does it take so long to replace a damaged pressure gauge? It should have been replaced by now & defect closed out."]
[null,null,null,null,7315,"91_15/12/2019 4:25:24 PM","2019-12-11","Defect","Ship Staff","Ship Staff Insp.","Pressure guage from the bridge wing fire line is missing and blanked.","Accommodation","LSA / FFA Appliances","Behaviour Based,Human Error,Knowledge Based","","","","","Renewed.","2019-12-31","","Completed","2019-12-21","No","No","No","Internal","Since no RO raised for new pressure gauge, we assume that same is readily available on board.  If so, why same not fitted?"]
[null,null,null,null,7316,"91_15/12/2019 4:28:38 PM","2019-12-11","Defect","Ship Staff","Ship Staff Insp.","F-Keys from Fire Hyd. & Isolation V/Vs at various location Missing.","Deck - Pipe / Fittings","LSA / FFA Appliances","Behaviour Based,Human Error,Knowledge Based","","","","","Fabricated and put in place.","2019-12-31","","Completed","2019-12-22","No","No","No","Internal","Please update status of job progress to date."]
[null,null,null,null,7318,"91_15/12/2019 4:36:50 PM","2019-12-11","Defect,Defect","Ship Staff","Ship Staff Insp.","Pressure guage on port side bunker manifold broken.","E/R - Pipes/ valves & fittings","MARPOL Related","Behaviour Based,Equipment Related","","","","","Renewed.","2019-12-31","","Completed","2019-12-16","No","No","No","Internal","Since no RO issued for supply of new pressure gauge, we can only assume that the required pressure gauge is readliy avaiable on board. If so, why is it taking so long to replace same?"]
[null,null,null,null,7321,"91_14/12/2019 11:18:23 AM","2019-11-15","Defect","Ship Staff","Ship Staff Insp.","EGB Chemical soot blower line to the economiser found sheered and also line is completely choked","E/R - Boiler,E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","Pipe section removed and new line fabricated and put in place.","2019-12-31","","Completed","2019-12-14","No","No","No","Internal"]
[null,null,null,null,7322,"91_Tue Dec 10 2019 16:54:15 GMT+0000 (Coordinated Universal Time)","2019-12-07","Critical Equipment,Defect","Ship Staff","Ship Staff Insp.","During the monthly Calibration of Fixed Gas Detection System,Pumps for the Fixed Gas detection system not taking  suction.","Critical Equip.","Cargo / Ballast Systems","Equipment Related,Inappropriate Procedure,Knowledge Based","8.41","Very High","","","All pumps overhauled and system made operational. Tested from all locations and found working satisfactory.","2019-12-15","","Completed","2019-12-13","No","No","No","Internal"]
[null,null,null,null,7323,"91_15/12/2019 1:21:01 PM","2019-11-15","Defect","Ship Staff","Ship Staff Insp.","Suspect atmospheric condensor leaking as hotwell and boiler chloride ppm is very high. \t","Miscellaneous","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Atmospheric condensor opened up for inspection and found one tube had moved out of place and there was SW ingress from there. Tubes cleaned and pressure tested. Put back in use.","2019-12-31","","Completed","2019-12-11","No","No","No","Internal"]
[null,null,null,null,7324,"91_15/12/2019 1:44:53 PM","2019-11-30","Defect","Ship Staff","Ship Staff Insp.","Feed water inlet valve to Aux Boiler found leaking from the bonnet gasket","E/R - Boiler,E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","Bonnet gasket renewed after isolating the boiler","2019-12-15","","Completed","2019-12-02","No","No","No","Internal"]
[null,null,null,null,7325,"91_15/12/2019 4:10:52 PM","2019-12-05","Defect","Ship Staff","Ship Staff Insp.","Drains at Bridge entrances chocked.","Accommodation","General Appearance","Behaviour Based,Human Error","","","","","To be Made free.","2019-12-20","","Completed","2019-12-14","No","No","No","Internal"]
[null,null,null,null,7326,"91_15/12/2019 4:34:30 PM","2019-12-11","Defect","Ship Staff","Ship Staff Insp.","Fire hose is damaged in Fire hose box number 3","LSA / FFA","Emgcy. Systems","Behaviour Based,Equipment Related","","","","","Fire hose needs to be replaced with new one.","2019-12-15","","Completed","2019-12-12","No","No","No","Internal"]
[null,null,null,null,7327,"91_16/12/2019 1:46:20 PM","2019-12-14","Defect","Ship Staff","Ship Staff Insp.","ACCOMMODATION GAS DETECTOR OFFICER SMOKE ROOM AND UPPER DECK PORT SIDE NOT WORKING","Accommodation","General Appearance","Equipment Related","","","","","TO BE CALIBRATE BY SHIP STAFF","2019-12-16","","Completed","2019-12-15","No","No","No","Internal"]
[null,null,null,null,7328,"91_16/12/2019 1:49:24 PM","2019-12-13","Defect","Ship Staff","Ship Staff Insp.","Weldin pump suction hose broken","Miscellaneous","General Appearance","Equipment Related","","","","","replaced new suction hose","2019-12-13","","Completed","2019-12-13","No","No","No","Internal"]
[null,null,null,null,9284,"91_22/12/2019 11:36:29 PM","2019-12-15","Defect","Ship Staff","Ship Staff Insp.","Atmospheric condensor condensate line to cascade tank found leaking from gasket.\t","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Gasket renewed and leak rectified.","2019-12-31","","Completed","2019-12-22","No","No","No","Internal"]
[null,null,null,null,null,"91_20/11/2019 1:18:33 AM","2019-10-27","Defect","Ship Staff","Ship Staff Insp.","ER tank top condition is bad state","Miscellaneous","General Appearance","Equipment Related",10.29,"Medium","Not Applicable","Not Applicable","Engine room bottom platform and bilge wells cleaning and painting job carried out.","2020-01-15",null,"Completed","2020-01-07","No",null,null,"Internal"]
[null,null,null,null,null,"91_7/1/2020 4:34:12 PM","2020-01-06","Defect","Ship Staff","Ship Staff Insp.","E/R AFT STBD BLOWER FLAP FOUND NOT FULLY CLOSING.","Miscellaneous","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","VENT FLAP AIR PISTON DISTANCE ADJUSTED, NOW ITS FULLY CLOSING.","2020-01-10",null,"Completed","2020-01-07","No",null,null,"Internal"]
[null,null,null,null,null,"91_7/1/2020 4:42:34 PM","2019-12-31","Defect","Ship Staff","Ship Staff Insp.","PORT FWG EJECTOR PUMP SUCTION PIPE BENT FOUND PIN HOLE LEAK. ","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","NEW PIPE FABRICATION CARRIED OUT AND FITTED BACK.","2020-01-05",null,"Completed","2020-01-01","No",null,null,"Internal"]
[null,null,null,null,null,"91_Wed Dec 11 2019 02:28:44 GMT+0000 (Coordinated Universal Time)","2019-10-27","Defect","Ship Staff","Ship Staff Insp.","VDR Data Playback software not available onboard.","Navigation - VDR / BNWAS","Navigation","Equipment Related",4.1100000000000003,"Medium","Not Applicable","Not Applicable","Required VDR Playback software.--->VDR Software Recvd onboard,Installed & Tested.Satisfactory","2019-12-31",null,"Completed","2020-01-03","No",null,null,"Internal"]
[null,null,null,null,null,"91_19/11/2019 7:23:14 PM","2019-10-27","Defect,Defect","Ship Staff","Ship Staff Insp.","Severall pressure and temperature gauges found defective in ER. Separate list for the same will be sent to office in due time.","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","ALL DEFECTIVE PRESSSURE AND TEMP. GAUGES REPLACED WITH NEW ONES, ALL FOUND WORKING IN ORDER ","2020-02-01",null,"Completed","2020-01-19","No",null,null,"Internal"]
[null,null,null,null,null,"91_20/11/2019 1:12:03 AM","2019-10-27","Defect","Ship Staff","Ship Staff Insp.","Sludge tank capacity very low and doesn't commensurate with the sludge generation on board. All pumps in ER are of gland seal type.","Hull & Tanks,Miscellaneous","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","SLUDGE MANAGEMENT ARE UNDER CONTROL, CONTINUOUS BURNING OF SLUDGE IS BEING CARRIED OUT, MONITORING SLUDGE PRODUCTION EVERYDAY.","2020-03-31",null,"Completed","2020-01-19","No",null,null,"Internal"]
[null,null,null,null,null,"91_20/11/2019 6:21:24 AM","2019-10-27","Defect","Ship Staff","Ship Staff Insp.","Composite boiler emergency firing system not operational","E/R - Boiler","Emgcy. Systems","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","BOILER EMERGENCY FIRING MADE OPERATIONAL, NOW WORKING SATISFACTORY.","2020-01-31",null,"Completed","2020-01-16","No",null,null,"Internal"]
[null,null,null,null,null,"91_20/11/2019 1:03:33 AM","2019-10-30","Defect","Ship Staff","Ship Staff Insp.","There is no Sewage Holding tank onboard","E/R - Aux. Mach.","Eng. / Strg. Comp.","Industry Issue",null,null,"Not Applicable","Not Applicable","This job to be deferred to DD. Job description already transferred to REFMAN .","2021-04-30",null,"Completed","2020-01-20","Yes",null,null,"Internal"]
[null,null,null,null,null,"91_15/12/2019 3:20:49 PM","2019-12-01","Defect","Ship Staff","Ship Staff Insp.","Sewage drain pipe leading to STP has leaks at several places.","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","This job should be refered to DD. Job description already transferred to REFMAN.","2021-01-31",null,"Completed","2020-01-20","Yes",null,null,"Internal"]
[null,null,null,null,null,"91_20/1/2020 4:48:43 PM","2019-10-24","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Engine Room Bilge wells to be cleaned and oil free.","Hull & Tanks,Miscellaneous","MARPOL Related","Equipment Related",10.29,"Medium","Not Applicable","Not Applicable","Engine Room bilge wells cleaned and painted","2019-11-24",null,"Completed","2019-11-12","No",null,null,"Internal"]
[null,null,null,null,null,"91_20/1/2020 5:04:33 PM","2019-10-24","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Vent Heads to be inspected for all WBT","Deck - Pipe / Fittings,Hull & Tanks","Cargo / Ballast Systems","Equipment Related",11.7,"High","Not Applicable","Not Applicable","All vent heads inspected and found in good condition.","2019-12-20",null,"Completed","2019-12-17","No",null,null,"Internal"]
[null,null,null,null,null,"91_20/1/2020 5:07:33 PM","2019-10-24","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Composite Boiler Inspection and cleaning.\t","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","Boiler inspection and cleaning carried out.","2019-11-24",null,"Completed","2019-11-23","No",null,null,"Internal"]
[null,null,null,null,null,"91_20/1/2020 5:15:15 PM","2019-10-24","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Glycol Pump No.2 making noise, needs to overhaul.\t","Cargo Mach.","Eng. / Strg. Comp.","Equipment Related",8.33,"High","Not Applicable","Not Applicable","Pump overhauled and made operational","2019-11-24",null,"Completed","2019-11-15","No",null,null,"Internal"]
[null,null,null,null,null,"91_20/1/2020 5:19:40 PM","2019-10-24","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Steam leaks to arrest.","E/R - Boiler,E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","Various leaks idetified and gaskets renewed as required.","2019-12-15",null,"Completed","2019-11-26","No",null,null,"Internal"]
[null,null,null,null,null,"91_20/1/2020 5:22:52 PM","2019-10-24","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","ME Scavange inspection to carry out","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","ME Scavange inspection to carried out","2019-11-24",null,"Completed","2019-11-23","No",null,null,"Internal"]
[null,null,null,null,null,"91_20/1/2020 5:27:19 PM","2019-10-24","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","LT coolers to open up and clean","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","LT coolers cleaned.","2019-11-30",null,"Completed","2019-11-26","No",null,null,"Internal"]
[null,null,null,null,null,"91_20/1/2020 5:30:11 PM","2019-10-24","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Cargo Plant Expansion valves to overhaul and put back in Auto mode.\t","Cargo Mach.","Cargo / Ballast Systems","Equipment Related",8.33,"High","Not Applicable","Not Applicable","All cargo compressor expansion valves and floats overhauled and tried out comprssor in Auto mode. Working in satisfactory condition.","2019-12-31",null,"Completed","2019-12-30","No",null,null,"Internal"]
[null,null,null,null,null,"91_20/1/2020 5:33:54 PM","2019-10-24","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","FW tanks to empty and clean.","Hull & Tanks","MLC Related","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","Fresh water tanks cleaned.","2019-12-31",null,"Completed","2019-12-31","No",null,null,"Internal"]
[null,null,null,null,null,"91_20/1/2020 5:37:56 PM","2019-10-24","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Safety System for DGS to make operational","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","All safety trips and alarms on DGS made in operational condition.","2019-11-24",null,"Completed","2019-11-15","No",null,null,"Internal"]
[null,null,null,null,null,"91_20/1/2020 5:41:36 PM","2019-10-24","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Service Air compressor pressure sensor defective. To change and put in operation.","E/R - Air Comp.","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","Recerived spare pressure sensor fitted and compressor made in operational condition.","2019-11-24",null,"Completed","2019-11-16","No",null,null,"Internal"]
[null,null,null,null,null,"91_20/1/2020 5:44:19 PM","2019-11-24","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Purifier FW Header tanks leaking.","E/R - Purifier","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","Valve changed and gasket renewed.","2020-01-31",null,"Completed","2020-01-17","No",null,null,"Internal"]
[null,null,null,null,null,"91_20/1/2020 5:48:08 PM","2019-10-24","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Hose handling crane Hyd isolating valve very hard to operate. same to free","Deck - Mooring Machinery","Mooring","Behaviour Based,Equipment Related",8.73,"Medium","Not Applicable","Not Applicable","Hydraulic Isolating valve overhauled and made in operational condition.","2019-11-24",null,"Completed","2019-11-06","No",null,null,"Internal"]
[null,null,null,null,null,"91_20/1/2020 5:50:54 PM","2019-10-24","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Incinerator Waste oil tank vent line to check and clean.","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related",11.7,"High","Not Applicable","Not Applicable","Incinerator waste oil tank vent line cleaned.","2019-11-24",null,"Completed","2019-11-07","No",null,null,"Internal"]
[null,null,null,null,null,"91_20/1/2020 5:55:31 PM","2019-10-24","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Gangways(Both) very hard to bring in completely. To investigate and repair.\t","Miscellaneous","General Appearance","Equipment Related",11.4,"Very High","Not Applicable","Not Applicable","Gangway Air motor renewed with spare and greasing carried out and made in good operational condition.","2019-11-24",null,"Completed","2019-11-06","No",null,null,"Internal"]

{"sheet":"Calc","index":2,"n_rows":28,"n_cols":12,"rows_kept":28,"cut":false,"hidden":true,"merged":[]}
["Def_type","Def_cause","Equipments","VIQrefno","Observer_code"]
[]
[]
[]
[]
[null,null,null,null,null,null,null,null,null,null,null,"Dim itemSele As Long"]
[null,null,null,null,null,null,null,null,null,null,null,"   dim startRow as integer"]
[null,null,null,null,null,null,null,null,null,null,null,"   startRow=1"]
[null,null,null,null,null,null,null,null,null,null,null,"        For itemSele = 0 To ListBox1.ListCount - 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        If ListBox1.Selected(itemSele) = True Then"]
[null,null,null,null,null,null,null,null,null,null,null,"        Worksheets(\"WorksheetName\").Range(\"A\" & startRow).Value = ListBox1.List(itemSele)"]
[null,null,null,null,null,null,null,null,null,null,null,"        startRow = startRow + 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next"]
[null,null,null,null,null,null,null,null,null,null,null,"Dim LastRowA As String"]
[null,null,null,null,null,null,null,null,null,null,null,"        Dim itemSele As Long"]
[null,null,null,null,null,null,null,null,null,null,null,"       Dim startRow as integer"]
[null,null,null,null,null,null,null,null,null,null,null,"        LastRowA = ActiveSheet.Cells(Rows.count, \"A\").End(xlUp).row"]
[null,null,null,null,null,null,null,null,null,null,null,"        startQue = 0"]
[null,null,null,null,null,null,null,null,null,null,null,"        For itemSele = 0 To ListBox1.ListCount - 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        For startRow = 1 To LastRowA"]
[null,null,null,null,null,null,null,null,null,null,null,"        If Worksheets(\"WorksheetName\").Range(\"A\" & startRow).Value = ListBox1.List(itemSele) Then"]
[null,null,null,null,null,null,null,null,null,null,null,"        ListBox1.Selected(itemSele) = True"]
[null,null,null,null,null,null,null,null,null,null,null,"        Exit For"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next j"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]

{"sheet":"Areaofobs","index":3,"n_rows":17,"n_cols":2,"rows_kept":17,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Cargo / Ballast Systems",11]
["Cert. & Docu.",2]
["Communication",6]
["Crew Management",3]
["Emgcy. Systems",13]
["Eng. / Strg. Comp.",14]
["General Appearance",15]
["Ice Opns.",17]
["ISM Related",7]
["ISPS Related",10]
["LSA / FFA Appliances",8]
["MARPOL Related",9]
["MLC Related",4]
["Mooring",12]
["Navigation",5]
["Structural Condn. / WT integrity ",16]

{"sheet":"Vessel_type","index":4,"n_rows":1,"n_cols":2,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["Vessel_type","ID"]

{"sheet":"Deficiency_type","index":5,"n_rows":8,"n_cols":3,"rows_kept":8,"cut":false,"hidden":true,"merged":[]}
["TITLE","Type of deficiency_description","ID"]
["Breakdown",null,6]
["Critical Equipment",null,4]
["Defect",null,1]
["Guarantee Claim",null,8]
["Non Conformity",null,2]
["Observation",null,3]
["Other",null,7]

{"sheet":"VIQrefno","index":6,"n_rows":379,"n_cols":3,"rows_kept":379,"cut":false,"hidden":true,"merged":[]}
["VIQ_ref_no","Risk Value of observation","ID"]
["1.1","Low",10160]
["1.10","Low",10169]
["1.11","Low",10170]
["1.12","Low",10171]
["1.13","Low",10172]
["1.14","Low",10173]
["1.15","Low",10174]
["1.16","Low",10176]
["1.17","Low",10177]
["1.18","Low",10178]
["1.19","Low",10179]
["1.2","Low",10161]
["1.20","Low",10180]
["1.21","",10181]
["1.22","Low",10183]
["1.23","Low",10184]
["1.24","Low",10185]
["1.25","Low",10186]
["1.26","Low",10187]
["1.3","Low",10162]
["1.4","Low",10163]
["1.5","Low",10164]
["1.6","Low",10165]
["1.7","Low",10166]
["1.8","Low",10167]
["1.9","Low",10168]
["1.99","High",16296]
["10.1","Medium",10354]
["10.10","High",10363]
["10.11","Medium",10364]
["10.12","Very High",10365]
["10.13","Very High",10366]
["10.14","Medium",10367]
["10.15","Low",10368]
["10.16","Very High",10369]
["10.17","Very High",10370]
["10.18","High",10371]
["10.19","Very High",10372]
["10.2","Low",10355]
["10.20","High",10373]
["10.21","Medium",10374]
["10.22","Low",10375]
["10.23","Medium",10376]
["10.24","Low",10377]
["10.25","Very High",10378]
["10.26","High",10379]
["10.27","Medium",10380]
["10.28","Low",10381]
["10.29","Medium",10382]
["10.3","Medium",10356]
["10.30","High",10383]
["10.31","Very High",10384]
["10.32","Very High",10385]
["10.33","High",10386]
["10.34","High",10387]
["10.35","Very High",10388]
["10.36","Very High",10389]
["10.37","Medium",10390]
["10.38","Medium",10391]
["10.39","High",10392]
["10.4","High",10357]
["10.40","Medium",10393]
["10.41","Medium",10394]
["10.42","Medium",10395]
["10.43","Medium",10396]
["10.44","Medium",10397]
["10.45","Very High",10398]
["10.46","High",10399]
["10.47","Medium",10400]
["10.48","High",10401]
["10.49","Medium",10402]
["10.5","Low",10358]
["10.50","High",10403]
["10.51","Low",10404]
["10.52","Medium",10405]
["10.53","Medium",10406]
["10.54","High",10407]
["10.55","Low",10408]
["10.6","Very High",10359]
["10.7","Medium",10360]
["10.8","Medium",10361]
["10.9","Medium",10362]
["10.99","High",10409]
["11.1","High",10313]
["11.10","Medium",10322]
["11.11","Very High",10323]
["11.12","Low",10324]
["11.13","Low",10325]
["11.14","Medium",10326]
["11.15","Low",10327]
["11.16","Low",10328]
["11.17","Low",10329]
["11.2","Medium",10314]
["11.3","Medium",10315]
["11.4","Very High",10316]
["11.5","Medium",10317]
["11.6","Medium",10318]
["11.7","High",10319]
["11.8","Low",10320]
["11.9","Low",10321]
["11.99","High",10330]
["12.1","High",10331]
["12.10","High",10341]
["12.11","High",10342]
["12.12","High",10343]
["12.13","High",10344]
["12.14","High",10345]
["12.15","High",10346]
["12.16","High",10347]
["12.17","High",10348]
["12.18","High",10349]
["12.19","High",10350]
["12.2","High",10332]
["12.20","High",10351]
["12.21","High",10352]
["12.3","High",10334]
["12.4","High",10335]
["12.5","High",10336]
["12.6","High",10337]
["12.7","High",10338]
["12.8","High",10339]
["12.9","High",10340]
["12.99","High",10353]
["2.1","Very High",10190]
["2.1.9","Very High",16297]
["2.10","Medium",10198]
["2.11","Medium",10199]
["2.12","Low",10200]
["2.13","Low",10201]
["2.14","Low",10202]
["2.15","Low",10203]
["2.16","Medium",10204]
["2.2","Medium",10191]
["2.3","High",10189]
["2.4","Medium",10192]
["2.5","Medium",10193]
["2.6","Low",10194]
["2.7","High",10195]
["2.8","High",10196]
["2.9","Medium",10197]
["2.99","High",10205]
["3.1","High",10206]
["3.2","Very High",10207]
["3.3","High",10208]
["3.4","Low",10188]
["3.5","Medium",10209]
["3.6","High",10210]
["3.7","Very High",10211]
["3.8","Very High",10212]
["3.99","High",10213]
["4.1","High",10214]
["4.10","High",10223]
["4.11","Medium",10224]
["4.12","Very High",10225]
["4.13","Very High",10226]
["4.14","Very High",10227]
["4.15","Very High",10228]
["4.16","Very High",10229]
["4.17","Very High",10230]
["4.18","Very High",10231]
["4.19","Low",10232]
["4.2","Medium",10215]
["4.20","Very High",10233]
["4.21","High",10234]
["4.22","Low",10235]
["4.23","High",10236]
["4.24","High",10237]
["4.25","Low",10238]
["4.26","Low",10239]
["4.27","High",10240]
["4.3","Medium",10216]
["4.4","High",10217]
["4.5","Very High",10218]
["4.6","Medium",10219]
["4.7","High",10220]
["4.8","Medium",10221]
["4.9","Medium",10222]
["4.99","High",10241]
["5.1","Very High",10410]
["5.10","High",10419]
["5.11","Low",10420]
["5.12","Medium",10421]
["5.13","High",10422]
["5.14","Very High",10423]
["5.15","Medium",10424]
["5.16","Medium",10425]
["5.17","Very High",10426]
["5.18","High",10427]
["5.19","Medium",10428]
["5.2","Very High",10411]
["5.20","Medium",10429]
["5.21","Medium",10430]
["5.22","High",10432]
["5.23","Very High",10433]
["5.24","Very High",10434]
["5.25","Medium",10435]
["5.26","Medium",10436]
["5.27","Medium",10437]
["5.28","Very High",10438]
["5.29","High",10439]
["5.3","Low",10412]
["5.30","High",10440]
["5.31","High",10441]
["5.32","High",10442]
["5.33","High",10443]
["5.34","Low",10444]
["5.35","Medium",10445]
["5.36","Low",10446]
["5.37","Low",10447]
["5.38","High",10448]
["5.39","Very High",10449]
["5.4","High",10413]
["5.40","Very High",10450]
["5.41","Very High",10451]
["5.42","Medium",10452]
["5.43","High",10453]
["5.44","High",10454]
["5.45","Medium",10457]
["5.46","Medium",10458]
["5.47","Low",10459]
["5.48","Medium",10460]
["5.5","Low",10414]
["5.6","Low",10415]
["5.7","Medium",10416]
["5.8","Medium",10417]
["5.9","Very High",10418]
["5.99","High",10461]
["6.1","Medium",10242]
["6.10","Low",10251]
["6.11","High",10252]
["6.12","Medium",10253]
["6.13","Low",10254]
["6.14","High",10255]
["6.15","High",10256]
["6.16","Very High",10257]
["6.17","Very High",10258]
["6.18","Medium",10259]
["6.19","Low",10260]
["6.2","High",10243]
["6.20","Medium",10261]
["6.21","High",10262]
["6.22","Medium",10263]
["6.3","Low",10244]
["6.4","High",10245]
["6.5","Low",10246]
["6.6","Medium",10247]
["6.7","High",10248]
["6.8","High",10249]
["6.9","Low",10250]
["6.99","High",10264]
["7.1","High",10265]
["7.10","High",10274]
["7.11","High",10275]
["7.12","High",10276]
["7.13","Medium",10277]
["7.14","Medium",10278]
["7.15","High",10279]
["7.16","High",10280]
["7.17","High",10281]
["7.2","High",10266]
["7.3","Low",10267]
["7.4","Low",10268]
["7.5","Low",10269]
["7.6","Medium",10270]
["7.7","Low",10271]
["7.8","High",10272]
["7.9","High",10273]
["7.99","High",10282]
["8.1","Very High",10462]
["8.10","Very High",10471]
["8.11","Very High",10472]
["8.12","Medium",10473]
["8.13","High",10474]
["8.14","Very High",10475]
["8.15","Medium",10476]
["8.16","Medium",10477]
["8.17","Very High",10478]
["8.18","High",10479]
["8.19","Very High",10480]
["8.2","Medium",10463]
["8.20","Very High",10481]
["8.21","Very High",10482]
["8.22","High",10483]
["8.23","Medium",10484]
["8.24","High",10485]
["8.25","High",10486]
["8.26","Medium",10487]
["8.27","Medium",10488]
["8.28","High",10489]
["8.29","Medium",10491]
["8.3","Medium",10464]
["8.30","Very High",10492]
["8.31","Very High",10493]
["8.32","High",10494]
["8.33","High",10495]
["8.34","Very High",10496]
["8.35","Very High",10497]
["8.36","Very High",10498]
["8.37","Very High",10500]
["8.38","Very High",10501]
["8.39","Very High",10502]
["8.4","Medium",10465]
["8.40","Very High",10503]
["8.41","Very High",10504]
["8.42","Very High",10505]
["8.43","Very High",10506]
["8.44","Medium",10508]
["8.45","High",10509]
["8.46","High",10510]
["8.47","Medium",10511]
["8.48","Very High",10512]
["8.49","Medium",10513]
["8.5","Medium",10466]
["8.50","High",10514]
["8.51","Very High",10515]
["8.52","Very High",10516]
["8.53","Very High",10517]
["8.54","High",10518]
["8.55","High",16222]
["8.56","Very High",16223]
["8.57","Very High",16224]
["8.58","Very High",16225]
["8.59","Medium",16226]
["8.6","Very High",10467]
["8.60","Medium",16227]
["8.61","Medium",16228]
["8.62","Very High",16229]
["8.63","Very High",16230]
["8.64","High",16231]
["8.65","Very High",16232]
["8.66","Medium",16233]
["8.67","Medium",16234]
["8.68","Medium",16235]
["8.69","Very High",16236]
["8.7","High",10468]
["8.70","Very High",16237]
["8.71","Medium",16238]
["8.72","Very High",16239]
["8.73","Medium",16240]
["8.74","High",16241]
["8.75","High",16242]
["8.76","Medium",16243]
["8.77","Medium",16244]
["8.78","Medium",16245]
["8.79","Very High",16246]
["8.8","High",10469]
["8.9","Very High",10470]
["8.99","High",16266]
["9.1","Low",10283]
["9.10","Medium",10292]
["9.11","Medium",10293]
["9.12","Medium",10294]
["9.13","Low",10295]
["9.14","Medium",10296]
["9.15","Medium",10297]
["9.16","High",10298]
["9.17","High",10299]
["9.18","Low",10300]
["9.19","Low",10301]
["9.2","Very High",10284]
["9.20","Medium",10302]
["9.21","Medium",10303]
["9.22","Low",10304]
["9.23","Low",10305]
["9.24","Medium",10306]
["9.25","Low",10307]
["9.26","Low",10308]
["9.27","Low",10309]
["9.28","Medium",10310]
["9.29","Low",10311]
["9.3","Very High",10285]
["9.4","High",10286]
["9.5","High",10287]
["9.6","Low",10288]
["9.7","Medium",10289]
["9.8","Medium",10290]
["9.9","Medium",10291]
["9.99","High",10312]

{"sheet":"Equipment_list","index":7,"n_rows":27,"n_cols":3,"rows_kept":27,"cut":false,"hidden":true,"merged":[]}
["TITLE","Equipment_list_description","ID"]
["Accommodation",null,12]
["Cargo Mach.",null,13]
["Critical Equip.",null,16]
["Deck - Machinery",null,18]
["Deck - Mooring Machinery",null,15]
["Deck - Pipe / Fittings",null,20]
["Documentation",null,21]
["E/R - Air Comp.",null,8]
["E/R - Aux. Engine",null,4]
["E/R - Aux. Mach.",null,7]
["E/R - Boiler",null,5]
["E/R - Main Engine",null,3]
["E/R - Pipes/ valves & fittings",null,9]
["E/R - Purifier",null,6]
["Elect. Mach. & Equip.",null,10]
["Hull & Tanks",null,19]
["Inert Gas",null,14]
["LSA / FFA",null,17]
["Miscellaneous",null,22]
["Navigation - DGPS / EPFS / AIS",null,28]
["Navigation - ECDIS",null,25]
["Navigation - Echo Sounder / Speed Log",null,26]
["Navigation - GMDSS & Communication",null,23]
["Navigation - Others",null,11]
["Navigation - RADAR",null,24]
["Navigation - VDR / BNWAS",null,30]

{"sheet":"PSC_MOU","index":8,"n_rows":11,"n_cols":3,"rows_kept":11,"cut":false,"hidden":true,"merged":[]}
["TITLE","PSC_MOU_description","ID"]
["Asia and the Pacific",null,2]
["Caribbean",null,4]
["Europe and the North Atlantic",null,1]
["Latin America",null,3]
["The Black Sea region",null,6]
["The Indian Ocean",null,8]
["The Mediterranean",null,7]
["The Riyadh MoU",null,9]
["USCG",null,10]
["West and Central Africa",null,5]

{"sheet":"Inspection_type","index":9,"n_rows":11,"n_cols":2,"rows_kept":11,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Bunkering Audit",14]
["Engineering Audit",16]
["ISM Audit",2]
["ISPS Audit",3]
["IT Audit",10]
["MLC Audit",1]
["Mooring Audit",9]
["Nav Audit / Verification",8]
["Ship Staff Insp.",15]
["Suptd. Insp.",13]

{"sheet":"Deficiency_Cause","index":10,"n_rows":8,"n_cols":3,"rows_kept":8,"cut":false,"hidden":true,"merged":[]}
["TITLE","Deficiency_Cause_description","ID"]
["Behaviour Based",null,1]
["Equipment Related",null,4]
["External Factors",null,5]
["Human Error",null,7]
["Inappropriate Procedure",null,8]
["Industry Issue",null,6]
["Knowledge Based",null,3]

{"sheet":"Observer_code","index":11,"n_rows":3,"n_cols":3,"rows_kept":3,"cut":false,"hidden":true,"merged":[]}
["TITLE","Observer_code_description","ID"]
["Owner / Marine / Tech. Suptd.",null,3]
["Ship Staff",null,2]

{"sheet":"Status_code","index":12,"n_rows":6,"n_cols":3,"rows_kept":6,"cut":false,"hidden":true,"merged":[]}
["TITLE","Status_code_description","ID"]
["Completed",null,6]
["Deferred to D D",null,5]
["In progress",null,3]
["Not Started",null,2]
["Waiting spare",null,4]

{"sheet":"PSC_ref_no","index":13,"n_rows":19,"n_cols":2,"rows_kept":19,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Alarms",9]
["Cargo operations including equipment",7]
["Certificates & Documentation",2]
["Dangerous Goods",13]
["Emergency Systems",5]
["Fire safety",8]
["ISM",16]
["ISPS",17]
["Life saving appliances",12]
["MLC, 2006",18]
["Other",19]
["Pollution Prevention",15]
["Propulsion and auxiliary machinery",14]
["Radio communication",6]
["Safety of Navigation",11]
["Structural condition",3]
["Water/Weathertight condition",4]
["Working and Living Conditions",10]

{"sheet":"Risk_value_of_obs","index":14,"n_rows":1,"n_cols":2,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["Risk Value of observation","ID"]

{"sheet":"Year","index":15,"n_rows":18,"n_cols":1,"rows_kept":18,"cut":false,"hidden":true,"merged":[]}
["Year"]
[2014]
[2015]
[2016]
[2017]
[2018]
[2019]
[2020]
[2021]
[2022]
[2023]
[2024]
[2025]
[2026]
[2027]
[2028]
[2029]
[2030]

{"sheet":"Month","index":16,"n_rows":13,"n_cols":1,"rows_kept":13,"cut":false,"hidden":true,"merged":[]}
["Month"]
["Jan"]
["Feb"]
["Mar"]
["Apr"]
["May"]
["Jun"]
["Jul"]
["Aug"]
["Sep"]
["Oct"]
["Nov"]
["Dec"]

{"sheet":"Date_","index":17,"n_rows":32,"n_cols":1,"rows_kept":32,"cut":false,"hidden":true,"merged":[]}
["Date"]
["01"]
["02"]
["03"]
["04"]
["05"]
["06"]
["07"]
["08"]
["09"]
[10]
[11]
[12]
[13]
[14]
[15]
[16]
[17]
[18]
[19]
[20]
[21]
[22]
[23]
[24]
[25]
[26]
[27]
[28]
[29]
[30]
[31]

{"sheet":"Sheet1","index":18,"n_rows":24,"n_cols":6,"rows_kept":24,"cut":false,"hidden":true,"merged":[]}
[]
[null,"ID","E",null,"Date Recorded",1]
[null,"UNIQUE ID","F",null,"Type of Deficiency",2]
[1,"Date Recorded","G",null,"Observer code",3]
["ignore","Vessel Type","H",null,"Type of Inspection",4]
[null,"Internal / External","I",null,"Description of Deficiency",5]
[null,"Drydock","J",null,"Equipment Categories",6]
[null,"Information Sharing","K",null,"Area of Observation",7]
[null,"Critical_item","L",null,"Deficiency Cause",8]
[null,"Deficiency Type","M",null,"VIQ Ref Number",9]
[null,"Deficiency Cause","N",null,"Risk Value of Obs",10]
[null,"Inspection Type","O",null,"PSC Ref Number",11]
[null,"Equipments","P",null,"PSC MOU ID",12]
[null,"VIQ Reference Number","Q",null,"Action Taken or Required",13]
[null,"Risk Value of the observation","R",null,"Target Date",14]
[null,"PSC Reference Number","S",null,"PO Ref No.",15]
[null,"PSC MOU","T",null,"Status Code",16]
[null,"Observer Code","U",null,"Date Completed",17]
[null,"Target Date","V",null,"Drydock",18]
[null,"Status Code","W",null,"Info Sharing",19]
[null,"Description of Deficiency","X",null,"Critical Item Flag",20]
[null,"Action taken / required","Y",null,"Audit Type",21]
[null,"PO ref no","Z"]
[null,"Date completed","AA"]

{"sheet":"Ship_information","index":19,"n_rows":2,"n_cols":3,"rows_kept":2,"cut":false,"hidden":true,"merged":[]}
["Ship_ID","Ship_Name","FILE_NAME"]
["91","APHRODITE (02-01-2020)","91_1577960435985.xlsm"]

{"sheet":"External_Deficiency_type","index":20,"n_rows":5,"n_cols":3,"rows_kept":5,"cut":false,"hidden":true,"merged":[]}
["TITLE","Type of deficiency_description","ID"]
["Condn of Class / Memo",null,5]
["Defect",null,1]
["Non Conformity",null,2]
["Observation",null,3]

{"sheet":"External_Inspection_type","index":21,"n_rows":10,"n_cols":2,"rows_kept":10,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Flag State Insp.",5]
["ISM Audit",2]
["ISPS Audit",3]
["MLC Audit",1]
["Nav Audit / Verification",8]
["OM Insp. (Eg. SIRE / CDI etc.)",6]
["Others (Eg. Insurance etc.)",12]
["PSC Inspection",4]
["Terminal Insp.",11]

{"sheet":"External_Observer_code","index":22,"n_rows":7,"n_cols":3,"rows_kept":7,"cut":false,"hidden":true,"merged":[]}
["TITLE","Observer_code_description","ID"]
["Class Surveyor",null,4]
["FSC Inspector",null,5]
["Others (Eg. Insurance etc.)",null,9]
["PSC Insp.",null,6]
["SIRE / CDI Insp.",null,8]
["Terminal Insp.",null,7]

{"sheet":"Sheet Version","index":23,"n_rows":2,"n_cols":2,"rows_kept":2,"cut":false,"hidden":true,"merged":[]}
["Version","Title"]
["2.0","Version 2.0"]